## Slide 1: Run 10 plan based on 25 Nov Revised Plan and s=200 extended by 1 week
Dec. 1, Begin cool down to 4.5K
Dec. 4, Cooldown to 4.5K complete in both rings!
Dec. 5, beam setup in RHIC begins.
Dec 16, 20 hr unplanned Maintenance day
Dec 20 (AM)-21(PM), blizzard 09 shut us down
Dec. 27, RHIC Setup complete, begin Ramp Up for Physics (was 14 Dec, late)
Dec 31 (midnight-store 11340), Machine, Physics declared (store 11340) s=200 GeV/n Au-Au
Jan 2 (midnight) STAR in Physics Mode
Jan 8 (0600) PHENIX in Physics Mode
Jan 12, Rebucketing not yet routine, stochastic cooling still to come.
Jan 22, changed beta* from 0.6 to 0.7 meters, rebucketing ~established, yellow transverse stochastic cooling on
Mar. 18 (0556), End 10 week s = 200 GeV/n Run, begin s = 62.4 GeV/n setup
Mar. 20 19, Begin 4 week s = 62.4 GeV/n run (gained a day of contingency)
  Machine physics 19 March for stores ≥11954
  PHENIX Physics 19 Mar for stores ≥11955
  STAR Physics 21 March for stores ≥11971(?)
Apr. 1716, End 4 week s = 62.4 GeV/n Run, begin s = 39 GeV/n setup
Apr. 19, Begin 1.5 week s = 39 GeV/n run
Apr. 30, End 1.5 week s = 39 GeV/n Run, begin n= 0.67 studies before polarity switches begin (i.e. this is a placeholder)
May 1, complete n= 0.67 studies for pp and s = 7.7 GeV/n setup (12 hr pol. switches)
May. 3, Begin 4 week s = 7.7 GeV/n run
May 23 – 28 IPAC (Kyoto)
May 22 Jun 3, Satogata is away
May 31, End 4 week s = 7.7 GeV/n Run, begin s = 11.5 GeV/n setup (4-6 hr polarity switch, if necessary)
Jun 2, begin s = 11.5 GeV/n for STAR
Jun 16, end 2 week s = 11.5 GeV/n run, begin s = 5 GeV/n setup (4-6 hr polarity switch, if necessary)
Jun 18, begin s = 5 GeV development
Jun 21, end 3 days at s = 5 GeV/n
Jun 22 , Begin Cryo Warm-up
Jun 23, Warm-up complete, Run 10 ends – 29.2 CRYO WEEKS

## Slide 2: Run 10 Au-Au Goals 3/17/10
STAR
  s = 62 GeV/n
    Luminosity Sampled/Delivered = ?/? mb-1
    100M Min-bias events
PHENIX
  s = 62 GeV/n
    Luminosity Recorded/Delivered = 193/64 mb-1
    400M Min-bias events

## Slide 3
PHENIX Goal (400M min-bias events)

## Slide 4
31 x 31 GeV/n Au
PHENIX BBLL1(vertex cut)
ZDC’s

## Slide 5
31 x 31 GeV/n Au horiz and vert emittances

## Slide 6
PHENIX Goal*
* With 20 cm sigma IR diamond
PHENIX Minimum Goal*
STAR Goal

## Slide 8
Average hours per week at store = 88.5

## Slide 10: Future Topics
Toward Smaller beta* - new quad triplets – D. Trbojevic

## Slide 11: Archive

## Slide 12
Through Jan 2010

## Slide 13
Through 2/28/10

## Slide 14
Ring | Bunches/Cycles | Avg Bunch in RHIC (10^6 ions) | Avg Efficiency XCBM to RHIC | XCBM to Uxf1 | Uxf1 to Wxf | Wxf to Arc | Arc to RHIC
Blue | 56/56 | 909 | 0.836 | 1.056 | 0.963 | 0.992 | 0.828
Yellow | 56/56 | 990 | 0.971 | 1.085 | 0.962 | 0.959 | 0.970
28 Feb Physics Store 11824, 0.7 m b* with some cooling and with rebucketing, STAR 32.7 mb-1, 3.9 hr store
Ring | Bunches/Cycles | Avg Bunch in RHIC (10^6 ions) | Avg Efficiency XCBM to RHIC | XCBM to Uxf1 | Uxf1 to Wxf | Wxf to Arc | Arc to RHIC
Blue | 111/28 | 1262 | 0.917 | 0.975 | 0.961 | 1.001 | 0.977
Yellow | 111/28 | 1246 | 0.910 | 0.961 | 0.964 | 0.988 | 0.994
0.905
0.989
0.961
1.023
0.879
1168
111/29
Yellow
0.927
0.999
0.961
1.024
0.911
1196
111/28
Blue
Arc to RHIC
Wxf to Arc
Uxf1 to Wxf
XCBM to Uxf1
Avg Efficiency XCBM to RHIC
Avg Bunch in RHIC (10^6 ions)
Bunches/Cycles
Ring
18 Jan Physics Store 11489, 0.6 m b* No cooling or rebucketing, STAR 22.6 mb-1, 3.9 hr store
Ring | Bunches/Cycles | Avg Bunch in RHIC (10^6 ions) | Avg Efficiency XCBM to RHIC | XCBM to Uxf1 | Uxf1 to Wxf | Wxf to Arc | Arc to RHIC
Blue | 111/28 | 1354 | 0.927 | 0.990 | 0.965 | 1.003 | 0.968
Yellow | 111/28 | 1377 | 0.931 | 0.990 | 0.964 | 0.989 | 0.987
2 Mar Physics Store 11834, 0.7 m b* with some cooling and with rebucketing, STAR 29.4 mb-1,3.9 hr store)
31 Dec 1st Physics Store 11340, 0.6 m b* No cooling or rebucketing, STAR 3.2 mb-1, 2.6 hr store

## Slide 15
Through 2/28/10

## Slide 16
Through 2/28/10

## Slide 17
 | Physics production or beam studies weeks | 
sNN (GeV) | 25-cryoweek run | 27-cryoweek run
200 | 10 | 10
62.4 | 4 | 4
39 | 1.5 | 1.5
27 | 0 | 0
18 | 0 | 0
11.5 @ STAR | 0 | 2
7.7 | 4 | 4
Beam studies @ 5 GeV and @  0.67 | 0.5 | 0.5
Revised Run 10 Plan, Nov 25, 2009

## Slide 18: Run 10 Au-Au Goals 11/19/09
STAR
  s = 200 GeV/n
    Luminosity Sampled/Delivered = 2/4 nb-1
    250M Central Events
    300M Min-bias events
PHENIX
  s = 200 GeV/n
    Luminosity Recorded/Delivered = 1.4/>6 nb-1
    Minimum Goal:
      Luminosity Recorded/Delivered = 1.1/3.9 nb-1

## Slide 19
Chart: Time from start of 4.5 deg cooldown to Physics
| Run 03 | Run 04 | Run 05 | Run 06 | Run 07 | Run 08 | Run 09 | Run 10
Actual | 6 | 6.5714 | 7.7143 | 4.5714 | 6 | 3.5714 | 4.5714
Goal | 3
Run 10 Actual | 1.2857