## Slide 1: Run 10 As Run
Dec. 1, Begin cool down to 4.5K
Dec. 4, Cooldown to 4.5K complete in both rings!
Dec. 5, beam setup in RHIC begins.
Dec 16, 20 hr unplanned Maintenance day
Dec 20 (AM)-21(PM), blizzard 09 shut us down
Dec. 27, RHIC Setup complete, begin Ramp Up for Physics (was 14 Dec, late)
Dec 31 (midnight-store 11340), Machine, Physics declared (store 11340) s=200 GeV/n Au-Au
Jan 2 (midnight) STAR in Physics Mode
Jan 8 (0600) PHENIX in Physics Mode
Jan 12, Rebucketing not yet routine, stochastic cooling still to come.
Jan 22, changed beta* from 0.6 to 0.7 meters, rebucketing ~established, yellow transverse stochastic cooling on
Mar. 18 (0556), End 10 week s = 200 GeV/n Run, begin s = 62.4 GeV/n setup
Mar. 19, Begin 4 week s = 62.4 GeV/n run
  Machine physics 19 March for stores ≥11954
  PHENIX Physics 19 Mar for stores ≥11955
  STAR Physics 22 March for stores ≥11976
Apr. 8, End 2.9 week s = 62.4 GeV/n Run, begin s = 39 GeV/n setup
Apr. 9, Begin 1.5 week s = 39 GeV/n run
  Machine physics 9 April for stores ≥12119
  PHENIX and STAR Physics 9 April for stores ≥12122
Apr. 14, 24 hours APEX for n= 0.67 studies
Apr. 22, End 1.9 week s = 39 GeV/n Run
Apr 22, Begin s = 7.7 GeV/n setup (12 hr pol. switches)
Apr 24 (fill 12238, 2300 hrs), Begin 4 week s = 7.7 GeV/n run
13 May ½ Sextupole Polarity Switch
May 17 s = 5 GeV/n development, 8 hour block
May 27 End 4.7 week s = 7.7 GeV/n Run, begin s = 11.5 GeV/n setup (No polarity switch required)
May 28 (0630), begin s = 11.5 GeV/n for STAR with store # 14266
Jun 7 (0800), end 2 (1.4 weeks) week s = 11.5 GeV/n run
Jun 7, resume s = 5 GeV development
Jun 8 (1800), end 5 GeV development, Begin Cryo Warm-up
Jun 11, Warm-up complete, Run 10 ends – 27.6 CRYO WEEKS
Last Week of June – Commissioned EBIS with He beam to booster

## Slide 3
PHENIX Goal*
* With 20 cm sigma IR diamond
PHENIX Minimum Goal*
STAR Goal

## Slide 5
PHENIX Goal (400M min-bias events)
STAR Goal (100M min-bias events)
19 Mar

## Slide 9
PHENIX BUR
STAR BUR
(Actual 2.9 weeks, 660M)
Actual Average ZDC Rate ~1200 Hz
(Actual 1.9 weeks, 250M)
(Actual 1.9 weeks, ~250M)
(Actual 4.7 weeks, ~5M)
Actual Average good event
rate ~6 Hz