## Slide 1: Run 11 RHIC Machine/Experiments Meeting
17 May 2011
Agenda:
√s = 200 GeV AuAu progress

## Slide 2: Run 11 Plan based on PAC recommendation/ALD Guidance and available funds 5/17/10 update
3 Jan, Begin cool-down to 4.5K
8 Jan, Cool-down to 4.5K complete in both rings, preliminary setup begins
24 Jan, 1 week Ramp-up with 8 hr/night beam to experiments
11 Feb (machine and ~experiments), begin ~10 week physics run (√s = 500 GeV pp)
7 Mar, cryo troubles, extended maintenance, 0900 hrs till 2000 hrs 14 Mar – lost 7.5 days
17 Mar, power distribution problem, extended maintenance, 1930 hrs till 0315 hrs 20 Mar – lost 2.3 days
18 Apr, end 9.4 week physics run at √s = 500 GeV
18 Apr jet target polarization measurement at injection (<5%)
19 Apr, short maintenance followed by setup for √s = 18 GeV AuAu
23 Apr, begin ~1 week physics run (√s = 19.6 AuAu)
2 May 08:00, end 1.3 week physics run at √s = 19.6 GeV
2 May, begin setup for √s = 200 AuAu
5 May, begin 2 day Ramp-up with 8 hr/night beam to experiments
6 May 11:37, begin ~8 week physics run at (√s = 200 GeV/n AuAu)
17 May- TODAY
29 June, end 7.7 week AuAu physics run at √s = 200 GeV/n , begin warm-up
30 June, cryo warm-up ~ complete, end 25.4 weeks cryo operation
What’s missing :
Run into July?
Uranium test/physics run
Low energy test run
only 2 days!

## Slide 3: √S = 200 GeV/n AuAu luminosity goals (to be updated)
STAR
2000 mb-1 sampled / 60% = 3300 mb-1 delivered
PHENIX
700 mb-1 sampled / ?% = ? mb-1 delivered
Estimate from PHENIX Beam Use Proposal
Live Time = 97%
Uptime = 65%
+/- 10 cm vertex = 25%

## Slide 4
STAR Goal
(with corrected STAR singles correction)

## Slide 5
(with corrected STAR singles correction)

## Slide 6
“Typical” Store 15865, 111/111 bunches, 0.75 (goal 0.65) m b*, Longitudal cooling only
1.1 x 109/bunch (goal = 1.1 x 109)
42 x 1026 s-1cm-2 (Goal = 45 x 1026)
PHENIX Lstore avg = 15 x 1026 s-1cm-2 (Goal = 25 x 1026 s-1cm-2)
Assumes 9.6 barn ZDC xsection
(singles corrected)
Ratio=1.18
Ratio=1.75
STAR SINGLES CORRECTION IS NOT RIGHT

## Slide 7
(not singles corrected)
Goal 17-20

## Slide 8
Latest Stores
goals
initial
average

## Slide 9
Through 16 May 2011

## Slide 10
Through 16 May 2011

## Slide 11
Through 16 May 2011
Possible oil contamination in one of the heat exchangers

## Slide 12
Through 16 May 2011

## Slide 13
Old information

## Slide 15
Final Lumi should change as it appears there’s an issue with the singles correction

## Slide 17: Run 11 Plan based on PAC recommendation/ALD Guidance and available funds 4/26/10 update (1/2)
3 Jan, Begin cool-down to 4.5K
8 Jan, Cool-down to 4.5K complete in both rings, preliminary setup begins
~11 Jan, 2 ⅟2 weeks beam setup for √s = 500 GeV pp in RHIC begins.
15 Jan, power supply work/DX training complete
17 Jan, first successful ramp
19 Jan, 1st maint day
24 Jan, 1 week Ramp-up with 8 hr/night beam to experiments
11 Feb (machine and ~experiments), begin ~10 week physics run (√s = 500 GeV pp)
16 Feb, AGS Jump Quads in routine operation for RHIC injection
24 Feb, 9 MHz cavity in routine operation
7 Mar, cryo troubles, extended maintenance, 0900 hrs till 2000 hrs 14 Mar – lost 7.5 days
17 Mar, power distribution problem, extended maintenance, 1930 hrs till 0315 hrs 20 Mar – lost 2.3 days
28 March – 1 April, PAC 2011
15 April Continuing Resolution Ends, guidance to follow
18 Apr, end 9.4 week pp physics run at √s = 500 GeV
18 Apr jet target polarization measurement at injection (<5%)
19 Apr, short maintenance followed by setup for √s = 18 GeV AuAu
23 Apr, begin ~1 week physics run (√s = 19.6 AuAu)
2 May, end 1.3 week physics run at √s = 19.6 GeV

## Slide 18
7 April Up-Down Ramp measurement
Blue Beam
Current CNI average analyzing powers are:
Energy AN
24 0.0144
100 0.0122
250 0.0147

## Slide 19
7 April Up-Down Ramp measurement
Yellow Beam (only Yellow 1 was
used as Yellow 2 was acting up)
Current CNI average analyzing powers are:
Energy AN
24 0.0144
100 0.0122
250 0.0147

## Slide 23
A good store with 9 MHz
Sat 2/26

## Slide 24
Run 11, First overnight store, Mon Jan 24 00:12
Fill number 14919,, s=500 GeV
21 days since start of cool-down
20K
20 x 1011
28 x 27 bunches
b*=0.65 meters
For peak store lumi = 170 x 1030 cm-2s-1 (projected MAXIMUM)
ZDC Rate ~ 400K (assuming 2.4 mb n-pair xsection)

## Slide 25: Run 9, First overnight store at s=500 GeV 22 days after start of cool-down
56 x 56 bunches
b*=0.7 meters
40K
40 x 1011

## Slide 26
AGS pp log, 23 Feb 09, 00:26

## Slide 27
26 weeks

## Slide 28
PHENIX Goal (50% pol)
STAR Goal (50% pol)
Goals to be updated/corrected

## Slide 29: Run-11 Au-Au luminosity projections 100 GeV/nucleon
Assume 6 weeks to ramp-up for min, and 8 weeks for max (stoch. cooling re-commissioning). Expect Lavg up to 25x1026cm-2s-1 (+25%). [from Run-10 to max: b* = 0.75  0.65 m, Nb = 1.1  1.1x109, more cooling]
PHENIX Goal (0.7 recorded)
?? (complicated)
STAR Goal (TBD)
Goals to be updated/corrected