## Slide 1: Run 11 RHIC Machine/Experiments Meeting
19 Apr 2011
Agenda:
Wrap-up of 250 GeV pp run
Goals for √s = 18 GeV/n Au-Au run

## Slide 2: Run 11 RHIC Machine/Experiments Meeting decisions
11/23/2010, APEX: Agreed to new APEX schedule, 12 hour sessions (0800-2400) every other week away from maintenance days.
2/25/2011, CNI Polarimeters Normalization: Beginning with physics store 15239, changed CNI Polarimeter analyzing power to agree with jet target polarization measurements …18% lower polarization than before.
4/11-15/2011, End 250 GeV pp on18 April, switch to 18 GeV AuAu on after jet target polarization measurement at injection is completed

## Slide 3
Decisions (cont’)
3/25/2011: AnDY Collisions (W. Fischer, L. Bland, E. Aschenauer,
S. Vigdor):
  (1) A. Drees will test the sequence developed to address both orbit and tune effects of AnDY at the end of a store (or multiple stores if needed).
  (2) When the proper functioning of the sequence is demonstrated we will go back to a 1.05e11/bunch threshold, and increase every store by another 0.05e11/bunch until we reach a 10-20% luminosity impact on STAR and PHENIX. In the event the prescribed bunch intensity is not reached during the store then AnDY should be steered into collision during the last 30 minutes of the store.
  (3) When the tune scan on the ramp finishes (~2 more tune to test), we will increase the store length to 10h or more, (with PHENIX/STAR concurrence), with this AnDY will have more time available after turning on.

## Slide 4: Run 11 Plan based on PAC recommendation/ALD Guidance and 28.3 weeks cryo operation 4/19/10 update
3 Jan, Begin cool-down to 4.5K
8 Jan, Cool-down to 4.5K complete in both rings, preliminary setup begins
~11 Jan, 2 ⅟2 weeks beam setup for √s = 500 GeV pp in RHIC begins.
15 Jan, power supply work/DX training complete
17 Jan, first successful ramp
19 Jan, 1st maint day
24 Jan, 1 week Ramp-up with 8 hr/night beam to experiments
11 Feb (machine and ~experiments), begin ~10 week physics run (√s = 500 GeV pp)
16 Feb, AGS Jump Quads in routine operation for RHIC injection
24 Feb, 9 MHz cavity in routine operation
7 Mar, cryo troubles, extended maintenance, 0900 hrs till 2000 hrs 14 Mar – lost 7.5 days
17 Mar, power distribution problem, extended maintenance, 1930 hrs till 0315 hrs 20 Mar – lost 2.3 days
28 March – 1 April, PAC 2011
15 April Continuing Resolution Ends, guidance to follow
18 Apr, end 9.4 week physics run at √s = 500 GeV pp run
18 Apr jet target polarization measurement at injection (<5%) – STILL NO BUDGET GUIDANCE
19 Apr, short maintenance followed by setup for √s = 18 GeV AuAu
25 Apr, begin ~1 week physics run (√s = 18 AuAu)
2 May, end 1 week physics run at √s = 18 GeV
2 May, begin 1 week setup for √s = 200 AuAu
9 May, begin 1 week Ramp-up with 8 hr/night beam to experiments
16 May, begin ?? week physics run at (√s = 200 GeV/n AuAu)
4 Jul, completed 26 weeks cryo operations (7 weeks 200 GeV AuAu to this point)
What’s missing :
Uranium test/physics run
Low energy test run
cryo warm-up

## Slide 6
Final Lumi should change as it appears there’s an issue with the singles correction

## Slide 8
Run 11 projected maximum
Store 15443 (12 Apr)

## Slide 13
Blue average = 45.3 +/- 0.6%
Yellow Average = 45.8 +/- 0.6%
one store

## Slide 15
~ Best Store (scaling to 100 hrs at store), 12 April
8.2 hour store, 2.64 pb-1, peak lumi 143 x 1030 cm-2s-1
Bunched intensity at beginning of physics 1.64/1.63 x 10 11
Run 11 Projected maximum

## Slide 16
PHENIX with singles correction
no singles correction
-16%
-8%
-17%
Run 11 Projected maximum (170 x 1030 cm-2s-1)

## Slide 17
Inferred emittance = 20.7 pmmmr

## Slide 18
Estimate for 18 GeV/n

## Slide 19
Through 14 Apr 2011

## Slide 20
Through 14 Apr 2011

## Slide 21
Through 14 Apr 2011

## Slide 22
Through 14 Apr 2011

## Slide 23
Old information

## Slide 24
7 April Up-Down Ramp measurement
Blue Beam
Current CNI average analyzing powers are:
Energy AN
24 0.0144
100 0.0122
250 0.0147

## Slide 25
7 April Up-Down Ramp measurement
Yellow Beam (only Yellow 1 was
used as Yellow 2 was acting up)
Current CNI average analyzing powers are:
Energy AN
24 0.0144
100 0.0122
250 0.0147

## Slide 29
A good store with 9 MHz
Sat 2/26

## Slide 30
Run 11, First overnight store, Mon Jan 24 00:12
Fill number 14919,, s=500 GeV
21 days since start of cool-down
20K
20 x 1011
28 x 27 bunches
b*=0.65 meters
For peak store lumi = 170 x 1030 cm-2s-1 (projected MAXIMUM)
ZDC Rate ~ 400K (assuming 2.4 mb n-pair xsection)

## Slide 31: Run 9, First overnight store at s=500 GeV 22 days after start of cool-down
56 x 56 bunches
b*=0.7 meters
40K
40 x 1011

## Slide 32
AGS pp log, 23 Feb 09, 00:26

## Slide 33
26 weeks

## Slide 34
PHENIX Goal (50% pol)
STAR Goal (50% pol)
Goals to be updated/corrected

## Slide 35: Run-11 Au-Au luminosity projections 100 GeV/nucleon
Assume 6 weeks to ramp-up for min, and 8 weeks for max (stoch. cooling re-commissioning). Expect Lavg up to 25x1026cm-2s-1 (+25%). [from Run-10 to max: b* = 0.75  0.65 m, Nb = 1.1  1.1x109, more cooling]
PHENIX Goal (0.7 recorded)
?? (complicated)
STAR Goal (TBD)
Goals to be updated/corrected