## Slide 1: Run 11 RHIC Machine/Experiments Meeting
23 Nov 2010
Agenda:
Schedule Update – are we ready for a 27 Dec cool-down? - (all)
APEX – proposal for alternate schedule – M. Bai

## Slide 2
26 weeks

## Slide 3: Run 11 Plan based on PAC recommendation/ALD Guidance and 28.3 weeks cryo operation
27 Dec, Begin cool-down to 4.5K
2 Jan, Cool-down to 4.5K complete in both rings
2 Jan, 2 ⅟2 weeks beam setup for √s = 500 GeV pp in RHIC begins.
20 Jan (Thursday), 1 week Ramp-up with 8 hr/night beam to experiments
27 Jan, begin 10 week physics run (√s = 500 GeV pp)
28 March – 1 April, PAC 2011
7 Apr, end 10 week physics run at √s = 500 GeV pp run
7 Apr, begin 1 week setup for √s = 200 AuAu
14 Apr, begin 1 week Ramp-up with 8 hr/night beam to experiments
21 Apr, begin 8 week physics run at (√s = 200 AuAu)
16 Jun, end 8 week √s = 200 AuAu run
16 Jun, begin setup for √s = 192 GeV UU
23 Jun, begin 1⅟2 week physics run (√s = 192 UU)
27 June – completed 26 weeks of cryo operation, may be out of $$’s
3 Jul, end 1⅟2 week physics run at √s = 192 GeV
3 Jul, begin setup for √s = 18 GeV AuAu
4 Jul, begin 1 week physics run (√s = 18 AuAu)
11 Jul, end 1 week physics run at √s = 18 GeV
13 Jul, warm-up complete (28.3 weeks)
Possible additions:
Low energy test run

## Slide 6
PHENIX Goal (50% pol)
STAR Goal (50% pol)
Goals to be updated/corrected

## Slide 7: Run-11 Au-Au luminosity projections 100 GeV/nucleon
Assume 6 weeks to ramp-up for min, and 8 weeks for max (stoch. cooling re-commissioning). Expect Lavg up to 25x1026cm-2s-1 (+25%). [from Run-10 to max: b* = 0.75  0.65 m, Nb = 1.1  1.1x109, more cooling]
PHENIX Goal (0.7 recorded)
?? (complicated)
STAR Goal (TBD)
Goals to be updated/corrected