## Slide 1: Run 11 RHIC Machine/Experiments Meeting
25 Jan 2011
Agenda:
Updates

## Slide 2: Run 11 RHIC Machine/Experiments Meeting decisions
11/23/2010
Agreed to new APEX schedule, 12 hour sessions (0800-2400) every other week away from maintenance days.

## Slide 3: Run 11 Plan based on PAC recommendation/ALD Guidance and 28.3 weeks cryo operation 1/25/10 update
3 Jan, Begin cool-down to 4.5K
8 Jan, Cool-down to 4.5K complete in both rings, preliminary setup begins
~11 Jan, 2 ⅟2 weeks beam setup for √s = 500 GeV pp in RHIC begins.
15 Jan, power supply work/DX training complete
17 Jan, first successful ramp
19 Jan, maint day
27 24 Jan, 1 week Ramp-up with 8 hr/night beam to experiments
3 Feb, begin 10 week physics run (√s = 500 GeV pp)
4 March – Continuing Resolution Ends
28 March – 1 April, PAC 2011
14 Apr, end 10 week physics run at √s = 500 GeV pp run
14 Apr, begin 1 week setup for √s = 200 AuAu
21 Apr, begin 1 week Ramp-up with 8 hr/night beam to experiments
28 Apr, begin 8 week physics run at (√s = 200 AuAu)
23 Jun, end 8 week √s = 200 AuAu run
23 Jun, begin setup for √s = 192 GeV UU
30 Jun, begin 1⅟2 week physics run (√s = 192 UU)
4 July – completed 26 weeks of cryo operation, may be out of $$’s
10 Jul, end 1⅟2 week physics run at √s = 192 GeV
10 Jul, begin setup for √s = 18 GeV AuAu
11 Jul, begin 1 week physics run (√s = 18 AuAu)
18 Jul, end 1 week physics run at √s = 18 GeV
20 Jul, warm-up complete (28.3 weeks)
Possible additions:
Low energy test run

## Slide 4
Run 11, First overnight store, Mon Jan 24 00:12
Fill number 14919,, s=500 GeV
21 days since start of cool-down
20K
20 x 1011
28 x 27 bunches
b*=0.65 meters
For peak store lumi = 170 x 1030 cm-2s-1 (projected MAXIMUM)
ZDC Rate ~ 400K (assuming 2.4 mb n-pair xsection)

## Slide 5: Run 9, First overnight store at s=500 GeV 22 days after start of cool-down
56 x 56 bunches
b*=0.7 meters
40K
40 x 1011

## Slide 6
Through 23 Jan 2011

## Slide 7
Through 23 Jan 2011

## Slide 8
Through 23Jan 2011
1st maint day

## Slide 10
Old information

## Slide 11
AGS pp log, 23 Feb 09, 00:26

## Slide 12
26 weeks

## Slide 13
PHENIX Goal (50% pol)
STAR Goal (50% pol)
Goals to be updated/corrected

## Slide 14: Run-11 Au-Au luminosity projections 100 GeV/nucleon
Assume 6 weeks to ramp-up for min, and 8 weeks for max (stoch. cooling re-commissioning). Expect Lavg up to 25x1026cm-2s-1 (+25%). [from Run-10 to max: b* = 0.75  0.65 m, Nb = 1.1  1.1x109, more cooling]
PHENIX Goal (0.7 recorded)
?? (complicated)
STAR Goal (TBD)
Goals to be updated/corrected