## Slide 1: Run 11 RHIC Machine/Experiments Meeting
31 May 2011
Agenda:
√s = 200 GeV AuAu progress
Update on 250 GeV integrated Lumi

## Slide 2: Run 11 Plan based on PAC recommendation/ALD Guidance and available funds 5/31/10 update
3 Jan, Begin cool-down to 4.5K
8 Jan, Cool-down to 4.5K complete in both rings, preliminary setup begins
24 Jan, 1 week Ramp-up with 8 hr/night beam to experiments
11 Feb (machine and ~experiments), begin ~10 week physics run (√s = 500 GeV pp)
7 Mar, cryo troubles, extended maintenance, 0900 hrs till 2000 hrs 14 Mar – lost 7.5 days
17 Mar, power distribution problem, extended maintenance, 1930 hrs till 0315 hrs 20 Mar – lost 2.3 days
18 Apr, end 9.4 week physics run at √s = 500 GeV
18 Apr jet target polarization measurement at injection (<5%)
19 Apr, short maintenance followed by setup for √s = 18 GeV AuAu
23 Apr, begin ~1 week physics run (√s = 19.6 AuAu)
2 May 08:00, end 1.3 week physics run at √s = 19.6 GeV
2 May, begin setup for √s = 200 AuAu
5 May, begin 2 day Ramp-up with 8 hr/night beam to experiments
6 May 11:37, begin ~8 week physics run at (√s = 200 GeV/n AuAu)
31 May- TODAY
29 June, end 7.7 wk AuAu physics run at √s = 200 GeV/n , begin warm-up
30 June, cryo warm-up ~ complete, end 25.4 weeks cryo operation
What’s missing :
Run into July?
Uranium test/physics run
Low energy test run
~2 days – PREP TIME REQ’D, NEED DECISION SOON!

## Slide 3: √S = 200 GeV/n AuAu luminosity goals (24 May efficiencies)
STAR
2000 mb-1 sampled / 60% = 3300 mb-1 delivered
PHENIX
700 mb-1 sampled / 14% = 5000 mb-1 delivered
Estimate from PHENIX Beam Use Proposal – 15.8%
Live Time = 97%
Uptime = 65%
+/- 10 cm vertex = 25%

## Slide 4
STAR Goal
PHENIX Goal

## Slide 5
Goal
Goal

## Slide 6
Goal
Fill 15974

## Slide 7
Fill 15974, not singles corrected
Fill 15974, with singles correction
26%
6%

## Slide 8
Fill 15974
Goal 17-20
Goal 122
Peak Lumi goal 45 x 1026 cm-2s-1
Average Lumi goal 25 x 1026 cm-2s-1
Long emitt
x,y emitt
Blue/yellow ions

## Slide 9
Revised 5/26/2011
Singles Corrected (STAR probably not right)

## Slide 10
Example store comparing AnDY Lumi to STAR and PHENIX
Not singles corrected

## Slide 11
Lumi
PHENIX = 3.58E9/2.7mb = 1.32 pb-1
STAR = 3.20E9/2.9 mb = 1.10 pb-1
AnDY = 0.30E9/0.95 mb = 0.32 pb-1
b*’s
PHENIX ~0.7 m
STAR ~0.8 m
AnDY ~ 3 m
Example store comparing AnDY Lumi to STAR and PHENIX
AnDY Lumi ~consistent with larger b* (x4 less Lumi)
Not singles corrected

## Slide 12
i.e. there’s still an issue with singles corrections.

## Slide 14
Old information

## Slide 15
Through fill 15928 delivered 1474 mb-1
201 ub^-1 of 700 ub^-1 accumulated in 12cm vertex
 Efficiency = 201/1474 = 14%

## Slide 16
Through 16 May 2011

## Slide 17
Through 16 May 2011

## Slide 18
Through 16 May 2011
Possible oil contamination in one of the heat exchangers

## Slide 19
Through 16 May 2011

## Slide 20
Final Lumi should change as it appears there’s an issue with the singles correction

## Slide 22: Run 11 Plan based on PAC recommendation/ALD Guidance and available funds 4/26/10 update (1/2)
3 Jan, Begin cool-down to 4.5K
8 Jan, Cool-down to 4.5K complete in both rings, preliminary setup begins
~11 Jan, 2 ⅟2 weeks beam setup for √s = 500 GeV pp in RHIC begins.
15 Jan, power supply work/DX training complete
17 Jan, first successful ramp
19 Jan, 1st maint day
24 Jan, 1 week Ramp-up with 8 hr/night beam to experiments
11 Feb (machine and ~experiments), begin ~10 week physics run (√s = 500 GeV pp)
16 Feb, AGS Jump Quads in routine operation for RHIC injection
24 Feb, 9 MHz cavity in routine operation
7 Mar, cryo troubles, extended maintenance, 0900 hrs till 2000 hrs 14 Mar – lost 7.5 days
17 Mar, power distribution problem, extended maintenance, 1930 hrs till 0315 hrs 20 Mar – lost 2.3 days
28 March – 1 April, PAC 2011
15 April Continuing Resolution Ends, guidance to follow
18 Apr, end 9.4 week pp physics run at √s = 500 GeV
18 Apr jet target polarization measurement at injection (<5%)
19 Apr, short maintenance followed by setup for √s = 18 GeV AuAu
23 Apr, begin ~1 week physics run (√s = 19.6 AuAu)
2 May, end 1.3 week physics run at √s = 19.6 GeV

## Slide 23
7 April Up-Down Ramp measurement
Blue Beam
Current CNI average analyzing powers are:
Energy AN
24 0.0144
100 0.0122
250 0.0147

## Slide 24
7 April Up-Down Ramp measurement
Yellow Beam (only Yellow 1 was
used as Yellow 2 was acting up)
Current CNI average analyzing powers are:
Energy AN
24 0.0144
100 0.0122
250 0.0147

## Slide 27
A good store with 9 MHz
Sat 2/26

## Slide 28
Run 11, First overnight store, Mon Jan 24 00:12
Fill number 14919,, s=500 GeV
21 days since start of cool-down
20K
20 x 1011
28 x 27 bunches
b*=0.65 meters
For peak store lumi = 170 x 1030 cm-2s-1 (projected MAXIMUM)
ZDC Rate ~ 400K (assuming 2.4 mb n-pair xsection)

## Slide 29: Run 9, First overnight store at s=500 GeV 22 days after start of cool-down
56 x 56 bunches
b*=0.7 meters
40K
40 x 1011

## Slide 30
AGS pp log, 23 Feb 09, 00:26

## Slide 31
26 weeks

## Slide 32
PHENIX Goal (50% pol)
STAR Goal (50% pol)
Goals to be updated/corrected

## Slide 33: Run-11 Au-Au luminosity projections 100 GeV/nucleon
Assume 6 weeks to ramp-up for min, and 8 weeks for max (stoch. cooling re-commissioning). Expect Lavg up to 25x1026cm-2s-1 (+25%). [from Run-10 to max: b* = 0.75  0.65 m, Nb = 1.1  1.1x109, more cooling]
PHENIX Goal (0.7 recorded)
?? (complicated)
STAR Goal (TBD)
Goals to be updated/corrected