## Slide 1
Run 12 RHIC Machine/Experiments Meeting
12 Jun 2012
Agenda:
Status Reports
Other business

## Slide 2: Run 12 Plan based on 20 weeks cryo operation 23 week schedule based on 4/10/12 Vigdor guidance, 6 June update
17 Jan, Begin cool-down to 4.5K
20 Jan, Cool-down to 4.5K in Blue and Yellow Ring complete, begin magnet setup
21-28 Jan, pp injection setup
28 Jan-3 Feb, LLRF, Ramp and store setup, begin 8 hr/night for experiments
3-10 Feb, 1 week ramp-up with 8 hrs/night for experiments
10 Feb, with store # 16397, begin 4 weeks pp physics with further ramp-up
16 Feb, 24/7 stores begin
12 (Monday) March, end 4.4 week pp physics √s = 200 GeV, begin ½ week setup for √s = 510 GeV pp
16 March, begin 5 week pp physics (machine only) √s = 510 GeV
17/18 March, STAR/PHENIX physics start with longitudal polarization
18 April (Wednesday 1300), end physics begin pp beam development/APEX
19 April (Thursday, 0800), end 4.9 week pp physics at √s = 510 GeV
19 April (Thursday, store 16580), begin 1 week setup for UU
22 April (evening) first overnight stores for experiments
25 April (Wednesday), begin 3 week UU physics run
15 May (Tuesday) end 2.9 week UU physics √s = 193 GeV/n, begin setup for √s = 200 GeV/n CuAu
18 May (Friday, store 16889) begin CuAu physics run
Today – 12 Jun
25 June (Monday, 08:00), end 5.5 week √s = 200 GeV/n CuAu run
25 June, begin √s = 5 GeV/n AuAu development
27 June (Wednesday, 08:00 – earlier if test complete) begin cryo warm-up
30 June, cryo warm-up complete (23.6 cryo-weeks)
Total Physics Weeks = 17.7

## Slide 3
PHENIX BUR Goal = 2.4 nb-1 sampled, ~11 delivered
STAR Goal = ~5 nb-1 sampled, ~8 nb-1 delivered
Goals

## Slide 4
Cu goal
Au goal
Through store 16979, 12 June
http://www.rhichome.bnl.gov/AGS/Operations/Run12/Run12_Lumi_100Cu_100Au.xlsx
and LogView

## Slide 5
Store 16889, 18 May (first physics store)
Average Lumi (Max) Goal
Peak Lumi (Max) Goal = 1.7 x 1028 cm-1s-1

## Slide 7
Other Slides

## Slide 9
Stores 16940 thru 16959

## Slide 10
PHENIX BUR Goal = 2.4 nb-1 sampled, ~11 delivered
STAR Goal = ~5 nb-1 sampled, ~8 nb-1 delivered

## Slide 12
Thru final store, 16735, 18 Apr

## Slide 14
PHENIX BUR Goal = 2.4 nb-1 sampled, ~11 delivered
STAR Goal = ~5 nb-1 sampled, ~8 nb-1 delivered

## Slide 16
Thru final store, 16735, 18 Apr

## Slide 17
368 mb-1

## Slide 18
STAR & PHENIX Goal

## Slide 19
Thru final store, 16735, 18 Apr
PHENIX Goal
STAR Goal

## Slide 20
~6 x 108 ions/bunch
~3 x 108 ions/bunch
~8.5 x 108 ions/bunch
Best store (16857) = 3.0 x 108 ions/bunch, blue/yellow beginning of store (physics)
STAR and PHENIX ~Goals

## Slide 21
Total in bank through April = $2,781K (CAD contribution = $1,360K)
Total CAD rebate to date = $625K (owed $735K)

## Slide 22
Thru 31 May

## Slide 23
Thru 31 May

## Slide 25
Thru 31 May

## Slide 27
Store 16889, 18 May (first physics store)
Average Lumi Max Goal
Average Lumi Max Goal

## Slide 28
Store, 16929, 28 May
Average Lumi Max Goal

## Slide 29
Store, 16940, 31 May
Average Lumi Max Goal

## Slide 30
Stores, 16928-30, 27-28 May

## Slide 31
The last vernier scan – note emittance issue with the PHENIX scan

## Slide 32
First store for detector tune-up

## Slide 33
Last three UU physics stores
~best store

## Slide 34
If 5 week run
PHENIX BUR Goal = 2.4 nb-1 sampled, ~8 delivered (?)
STAR Goal = ?
~8 nb-1

## Slide 35
First UU physics store, 16780, 25 April

## Slide 36
ion intensity minimum 111x6x108
ion intensity maximum 111x8.5x108
Transverse emittance projection
84/84bunches – 2.0/1.7 x 108 U/bunch
Setup Store, no rebucketing yet…
23 April 2012

## Slide 37
Blue weighted average = 50.3% ± 0.5%
Yellow weighted average = 53.4% ± 0.5%
average = 78.7%
Blue beam at injection jet target result = ? %

## Slide 40
Where we are with Uranium (From K. Zeno)
Into the booster 8 x 10^8 in 4 bunches
These are then combined into one bunch
Booster extraction 6.5 x 10^8 / bunch
30% efficiency into the AGS
AGS extraction is at 2 x 10^8 / bunch
Desired (Wolfram) ~ 7 x 10^8 / bunch
>>> 6 x 10^8 / bunch in RHIC
17 April 2012

## Slide 41
√s = 193 GeV/n UU – stores 16769 through 16775
Setup Stores, no rebucketing yet…

## Slide 43
4 Apr – 10 Apr stores

## Slide 44
STAR Goal for 5 weeks longitudal polarization (50% polarization):
  Sampled Luminosity = 45 pb-1 with 50% polarization
  Delivered Luminosity = 75 pb-1
PHENIX Goal for 5 weeks longitudal polarization (50% polarization):
  Sampled Luminosity = 30 pb-1 with |z| <30 cm
  = 10 pb-1 with |z| <10 cm
  Delivered Luminosity = 75 pb-1 changed to 120 pb-1, 3/29/12, Ed O’Brien email
Run 12, √s = 510 GeV polarized proton run – experiment goals

## Slide 45
27 Mar – 3 Apr stores

## Slide 46
Store 16632, Blue jet = 56.5 +/- 3.0; Yellow jet = 63.0 +/- 3.1
Best average polarization measured by jet for store > 8 hrs

## Slide 48
Store 16632
Average lumi goal
Peak lumi goal

## Slide 49
Store 16618, Blue jet = 51.0 +/- 3.2; Yellow jet = 32.6 +/- 3.3
Worst average polarization measured by jet for store > 8 hrs

## Slide 50
Store 16618

## Slide 51
Store 16587, Blue jet = 47.2 +/- 2.8; Yellow jet = 39.4 +/- 2.9
Next to worst average polarization measured by jet for store > 8 hrs

## Slide 52
Store 16587

## Slide 53
Store 16667, Blue jet = 58.1 +/- 2.9; Yellow jet = 60.7 +/- 3.1
Second best average polarization measured by jet for store > 8 hrs

## Slide 54
Store 16667
Average lumi goal
Peak lumi goal

## Slide 55
Table2: Max lumi parameters: 1.65x109/bunch, 0.6 b*, 20-25 mmmr emitt  peak = 200x1030 cm-2s-1
Average lumi goal
Peak lumi goal
Store 16632, 3/27/12

## Slide 56
23 Mar – 27 Mar stores

## Slide 58
All “physics” stores beginning with16570, 15 March
~Lstore avg Goal

## Slide 59
16592
16578
16586
From “StoreAnalysis” program in “StartUp”
Polarization Goal

## Slide 60
Expectation for 5 weeks physics:
45-95 pb-1 delivered luminosity with 45-50% polarization
P4L ~ 4 pb-1

## Slide 61
Blue Jet weighted average = 61.2% ± 0.5%; source blue average = 77.5%  20% lost
Yellow Jet weighted average = 55.8% ± 0.5%; source yellow average = 77.4%  28% lost
STAR & PHENIX Polarization Goals
Offline polarization is larger

## Slide 63
Target (max projection)
Best stores, 16475 and 16534

## Slide 64
Best stores, 16475 and 16534

## Slide 65
Fill 16475, 27 Feb, 8.9 hours physics store (10 hour Lumi on Store), PHENIX 1.03 pb-1

## Slide 66
Fill 16475, 27 Feb, 8.9 hours physics store (10 hour Lumi on Store), PHENIX 1.03 pb-1
beginning
end

## Slide 67
Fill 16475, 27 Feb, 8.9 hours physics store (10 hour Lumi on Store), PHENIX 1.03 pb-1
beginning
end

## Slide 68
Fill 16534, 9 Mar, 8.1 hours physics store (9.1 hr Lumi on store), PHENIX 1.04 pb-1

## Slide 69
Fill 16534, 9 Mar, 8.1 hours physics store (9.1 hr Lumi on store), PHENIX 1.04 pb-1
Beginning
End

## Slide 70
Fill 16534, 9 Mar, 8.1 hours physics store (9.1 hr Lumi on store), PHENIX 1.04 pb-1
Beginning
End

## Slide 72
Laverage(max)
(0.29 mb xsection)
Ions/bunch (max)
Past Week

## Slide 74
Run 12 Physics Stores to 28 Feb
Laverage(max)
(0.29 mb xsection)
Absolute scale should not be trusted)

## Slide 75
Store 16480 (27 Feb) – typical background issues
PHENIX
STAR
ZDC Singles
ZDC Singles
Protons/bunch
Protons/bunch
ZDC without and
with singles correction
ZDC without and
with singles correction

## Slide 76
Store 16480 (27 Feb) – typical background issues

## Slide 77
Store 16480 (27 Feb) – typical background issues

## Slide 78
Collision steering corrections background issues 26-27 Feb
ZDC Coincidence
ZDC Singles

## Slide 79
Lstore average(max)
Lpeak(max)
Example -- Store 16445, Sat Feb 18

## Slide 80
Blue Jet weighted average = 55.4 ± 0.5
Yellow Jet weighted average = 54.9 ± 0.5

## Slide 81
Run 12 projection for √s = 200 GeV pp
From Fischer et. Al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011
STAR Goal: 27 pb-1 delivered with 55-60 % polarization
PHENIX Goal: 27 pb-1 delivered with 55-60 % polarization
p2L = 8.2 pb-1 for 55% polarization

## Slide 82
First Physics Store (#16397, 04:01, 10 Feb)

## Slide 83
Today, 7 Feb 2012

## Slide 84
Typical Store from Run 9, 100 x 100 GeV pp

## Slide 85
Start cooldown
As of 16:18 hrs 20 Jan
3.5 days

## Slide 86
For Run 12 the PAC recommends the following (in order of priority):
5 weeks of running with polarized proton collisions at 200 GeV.
7 weeks of running with polarized proton collisions at 500 GeV.
5 weeks of running with Cu+Au collisions at 200 GeV.
3 weeks of running with U+U collisions at 193 GeV.
For Run13 the PAC recommends the following (not in order of priority):
12 weeks of running with polarized proton collisions at 500 GeV.
5 week of running with polarized proton collisions at 200 GeV.
7 weeks of running with Au+Au collisions at full energy.
Recommendations following the June 6-8, 2011 PAC

## Slide 87
D.L. November 23, 2011 update
Our helium supplier no longer able to meet our peek demand of 4 trailers in a one week period. They can give us one trailer a week starting on December 31st, so we expect to have all the helium we need, on time, but we will have to store most of it in the dewars outside 1006B. This will result in our 4K cooldown being a little less stable and predictable than it has been for the past few years when we received all of the helium at 1005R over a short period of time. Because of this, I expect the 4K cooldown will take a least one additional day.
Cryo Issue

## Slide 89
From Fischer et. al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011

## Slide 90
Run 12 projection for √s = 500 GeV pp
From Fischer et. Al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011

## Slide 91
Run 12 projection for √s = 193 GeV/n UU
From Fischer et. Al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011

## Slide 92
Run 12 projection for √s = 200 GeV/n CuAu
From Fischer et. Al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011