## Slide 1
Run 12 RHIC Machine/Experiments Meeting
13 Mar 2012
Agenda:
Status reports/goals for 255 x 255 GeV pp
Other business

## Slide 2: Run 12 Plan based on 20 weeks cryo operation –an example 20 week schedule based on Vincent’s pp start-up plans* Note physics weeks for 250 pp and HI are still to be determined
17 Jan, Begin cool-down to 4.5K
20 Jan, Cool-down to 4.5K in Blue and Yellow Ring complete, begin magnet setup
21-28 Jan, pp injection setup
28 Jan-3 Feb, LLRF, Ramp and store setup, begin 8 hr/night for experiments
3-10 Feb, 1 week ramp-up with 8 hrs/night for experiments
10 Feb, with store # 16397, begin 4 weeks pp physics with further ramp-up
16 Feb, 24/7 stores begin
12 (Monday) March, end 4.4 week √s = 200 GeV pp run, begin ½ week setup for √s = 500 GeV pp
Today – 13 Mar
15 March, begin ramp-up to √s = 500 GeV with 8 hrs/night for experiments
16 March, begin 5 week pp physics run at √s = 500 GeV
20 April, end 5 week pp physics run at √s = 500 GeV
If Uranium or Cu-Au…
20 April, begin 1 week setup for UU or CuAu (no overnight stores for experiments)
27 April, begin 5.1 week UU or CuAu physics run
20-25 May: IPAC
2 June end 5.1 week UU or CuAu physics run
2 June, begin cryo warm-up
5 June, cryo warm-up complete (20.0 cryo-weeks)
Total Physics Weeks = 14.5
* http://www.cadops.bnl.gov/AGS/Operations/OpsWiki/index.php/RHIC_Setup:_Polarized_Protons

## Slide 3
STAR & PHENIX Goal

## Slide 4
Blue Jet weighted average = 61.2% ± 0.5%; source blue average = 77.5%  20% lost
Yellow Jet weighted average = 55.8% ± 0.5%; source yellow average = 77.4%  28% lost
STAR & PHENIX Polarization Goals
Offline polarizations larger

## Slide 6
Target (max projection)
Best stores, 16475 and 16534

## Slide 7
Best stores, 16475 and 16534

## Slide 8
Fill 16475, 27 Feb, 8.9 hours physics store (10 hour Lumi on Store), PHENIX 1.03 pb-1

## Slide 9
Fill 16534, 9 Mar, 8.1 hours physics store (9.1 hr Lumi on store), PHENIX 1.04 pb-1

## Slide 10
Expectation for 5 weeks physics:
45-95 pb-1 delivered luminosity with 45-50% polarization
P4L ~ 4 pb-1

## Slide 12
As of 8 Mar 2012

## Slide 13
As of 8 Mar 2012

## Slide 15
Other Slides

## Slide 16
Laverage(max)
(0.29 mb xsection)
Ions/bunch (max)
Past Week

## Slide 17
$ in BNL Balanced Billing Bank for FY12 (through Jan) = +$1,157K
$48/MWhr

## Slide 19
Run 12 Physics Stores to 28 Feb
Laverage(max)
(0.29 mb xsection)
Absolute scale should not be trusted)

## Slide 20
Store 16480 (27 Feb) – typical background issues
PHENIX
STAR
ZDC Singles
ZDC Singles
Protons/bunch
Protons/bunch
ZDC without and
with singles correction
ZDC without and
with singles correction

## Slide 21
Store 16480 (27 Feb) – typical background issues

## Slide 22
Store 16480 (27 Feb) – typical background issues

## Slide 23
Collision steering corrections background issues 26-27 Feb
ZDC Coincidence
ZDC Singles

## Slide 24
Lstore average(max)
Lpeak(max)
Example -- Store 16445, Sat Feb 18

## Slide 25
Blue Jet weighted average = 55.4 ± 0.5
Yellow Jet weighted average = 54.9 ± 0.5

## Slide 26
Run 12 projection for √s = 200 GeV pp
From Fischer et. Al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011
STAR Goal: 27 pb-1 delivered with 55-60 % polarization
PHENIX Goal: 27 pb-1 delivered with 55-60 % polarization
p2L = 8.2 pb-1 for 55% polarization

## Slide 27
First Physics Store (#16397, 04:01, 10 Feb)

## Slide 28
Today, 7 Feb 2012

## Slide 29
Typical Store from Run 9, 100 x 100 GeV pp

## Slide 30
Start cooldown
As of 16:18 hrs 20 Jan
3.5 days

## Slide 31
For Run 12 the PAC recommends the following (in order of priority):
5 weeks of running with polarized proton collisions at 200 GeV.
7 weeks of running with polarized proton collisions at 500 GeV.
5 weeks of running with Cu+Au collisions at 200 GeV.
3 weeks of running with U+U collisions at 193 GeV.
For Run13 the PAC recommends the following (not in order of priority):
12 weeks of running with polarized proton collisions at 500 GeV.
5 week of running with polarized proton collisions at 200 GeV.
7 weeks of running with Au+Au collisions at full energy.
Recommendations following the June 6-8, 2011 PAC

## Slide 32
D.L. November 23, 2011 update
Our helium supplier no longer able to meet our peek demand of 4 trailers in a one week period. They can give us one trailer a week starting on December 31st, so we expect to have all the helium we need, on time, but we will have to store most of it in the dewars outside 1006B. This will result in our 4K cooldown being a little less stable and predictable than it has been for the past few years when we received all of the helium at 1005R over a short period of time. Because of this, I expect the 4K cooldown will take a least one additional day.
Cryo Issue

## Slide 34
From Fischer et. al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011

## Slide 35
Run 12 projection for √s = 500 GeV pp
From Fischer et. Al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011

## Slide 36
Run 12 projection for √s = 193 GeV/n UU
From Fischer et. Al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011

## Slide 37
Run 12 projection for √s = 200 GeV/n CuAu
From Fischer et. Al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011