## Slide 1: Run 12 RHIC Machine/Experiments Meeting
18 October 2011 (1st meeting)
Agenda:
Schedule issues (Pile)
Machine Status (Fischer)
STAR Readiness
PHENIX Readiness

## Slide 2
For Run 12 the PAC recommends the following (in order of priority):
5 weeks of running with polarized proton collisions at 200 GeV.
7 weeks of running with polarized proton collisions at 500 GeV.
5 weeks of running with Cu+Au collisions at 200 GeV.
3 weeks of running with U+U collisions at 193 GeV.
For Run13 the PAC recommends the following (not in order of priority):
12 weeks of running with polarized proton collisions at 500 GeV.
5 week of running with polarized proton collisions at 200 GeV.
7 weeks of running with Au+Au collisions at full energy.
Recommendations following the June 6-8, 2011 PAC

## Slide 3: Run 12 Plan based on PAC recommendation/ALD Guidance and 22 weeks cryo operation DRAFT-DRAFT
3 Jan, Begin cool-down to 4.5K
10 Jan, Cool-down to 4.5K complete in both rings begin √s = 200 GeV pp setup
17 Jan, begin 2 week ramp-up with 8 hrs/night for experiments
31 Jan, begin 5 weeks physics with further ramp-up
6 March, end 5 week √s = 200 GeV pp run, begin ½ week setup for √s = 500 GeV pp
10 March, begin 1 week ramp-up to √s = 500 GeV with 8 hrs/night for experiments
17 March, begin 7 week pp physics run at √s = 500 GeV
5 May, end 7 week pp physics run at √s = 500 GeV
17.4 cryo-weeks to this point, schedule beyond this point to be determined
If Uranium…
5 May, begin 1 week setup for √s = 193 GeV/n UU (no overnight stores for experiments)
12 May, begin 3 week √s = 193 GeV/n UU physics run
2 Jun, end 3 week √s = 193 GeV/n UU physics run
5 June, cryo warm-up complete (22.0 cryo-weeks)
Consistent with Fischer et. al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011

## Slide 4
beams/schedule
to be determined

## Slide 5
Cryogenic System Cool-down Projection based on Full Compressor Power Starting on January 3, 2012
10/17/11 – D. Lederle
.5 to 1 MW – Nov 10, 2011 through Dec 4, 2011 (temporary peaks up to 2 MW)
Scrub of RHIC rings and cryo plant, 14 atm pressure test of blue sextants 2/3 and 8/9 M-lines. Main compressor testing and scrub.
2.8 MW – Dec 5, 2011 through Jan 2, 2012
12/05/11 Start 45K cool-down of cryo plant
12/06/11 Start 45K wave in both RHIC rings
6 to 8 MW – Jan 3, 2012 through Jan 8, 2012
01/02/12 First liquid helium delivery
01/03/12 Start 4K wave in Blue ring, Hi potting (3 days)
01/04/12 Second liquid helium delivery
01/05/12 Third liquid helium delivery
01/06/12 Estimate blue ring cold and stable, soak complete, ready for magnet powering.
01/06/12 Start 4K wave in Yellow ring, Hi potting (3 days)
01/07/12 Fourth liquid helium delivery
01/08/12 Estimate yellow ring cold and stable, soak complete, ready for magnet powering.
5 MW starting on Jan 8, 2012
01/08/12 Start T7 turbine

## Slide 6
Other Slides

## Slide 7
From Fischer et. al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011

## Slide 8
Run 12 projection for √s = 200 GeV pp
From Fischer et. Al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011

## Slide 9
Run 12 projection for √s = 500 GeV pp
From Fischer et. Al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011

## Slide 10
Run 12 projection for √s = 193 GeV/n UU
From Fischer et. Al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011

## Slide 11
Run 12 projection for √s = 200 GeV/n CuAu
From Fischer et. Al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011