## Slide 1
Run 12 RHIC Machine/Experiments Meeting
20 Mar 2012
Agenda:
Status reports
APEX Update – M. Bai
Other business

## Slide 2: Run 12 Plan based on 20 weeks cryo operation –an example 20 week schedule based on Vincent’s pp start-up plans* Note physics weeks for 250 pp and HI are still to be determined
17 Jan, Begin cool-down to 4.5K
20 Jan, Cool-down to 4.5K in Blue and Yellow Ring complete, begin magnet setup
21-28 Jan, pp injection setup
28 Jan-3 Feb, LLRF, Ramp and store setup, begin 8 hr/night for experiments
3-10 Feb, 1 week ramp-up with 8 hrs/night for experiments
10 Feb, with store # 16397, begin 4 weeks pp physics with further ramp-up
16 Feb, 24/7 stores begin
12 (Monday) March, end 4.4 weeks √s = 200 GeV pp, begin ½ week setup for √s = 510 GeV pp
16 March, begin 5 week pp physics (machine only) √s = 510 GeV
? March, PHENIX and STAR physics start with longitudal polarization
Today – 20 March
(20+?) April, end 5 week pp physics run at √s = 500 GeV
If Uranium or Cu-Au…
(20+?) April, begin 1 week setup for UU or CuAu (no overnight stores for experiments)
27 April, begin (5.1-?) week UU or CuAu physics run
20-25 May: IPAC
2 June end (5.1-?) week UU or CuAu physics run
2 June, begin cryo warm-up
5 June, cryo warm-up complete (20.0 cryo-weeks)
Total Physics Weeks = 14.5
* http://www.cadops.bnl.gov/AGS/Operations/OpsWiki/index.php/RHIC_Setup:_Polarized_Protons

## Slide 3
STAR Goal for 5 weeks longitudal polarization (50% polarization):
  Sampled Luminosity = 45 pb-1 with 50% polarization
  Delivered Luminosity = 75 pb-1
PHENIX Goal for 5 weeks longitudal polarization (50% polarization):
  Sampled Luminosity = 30 pb-1 with |z| <30 cm
  = 10 pb-1 with |z| <10 cm
  Delivered Luminosity = 75 pb-1
Run 12, √s = 510 GeV polarized proton run – experiment goals

## Slide 4
Thru fill 16587, 19 Mar, assumes experiments started physics 17 Mar
Need to check this

## Slide 5
Exp goals
w/50%pol

## Slide 8
All “physics” stores beginning with16570, 15 March
~Lstore avg Goal

## Slide 9
16592
16578
16586
From “StoreAnalysis” program in “StartUp”
Polarization Goal

## Slide 10
Other Slides

## Slide 11
Expectation for 5 weeks physics:
45-95 pb-1 delivered luminosity with 45-50% polarization
P4L ~ 4 pb-1

## Slide 12
STAR & PHENIX Goal

## Slide 13
Blue Jet weighted average = 61.2% ± 0.5%; source blue average = 77.5%  20% lost
Yellow Jet weighted average = 55.8% ± 0.5%; source yellow average = 77.4%  28% lost
STAR & PHENIX Polarization Goals
Offline polarization is larger

## Slide 15
Target (max projection)
Best stores, 16475 and 16534

## Slide 16
Best stores, 16475 and 16534

## Slide 17
Fill 16475, 27 Feb, 8.9 hours physics store (10 hour Lumi on Store), PHENIX 1.03 pb-1

## Slide 18
Fill 16534, 9 Mar, 8.1 hours physics store (9.1 hr Lumi on store), PHENIX 1.04 pb-1

## Slide 20
As of 8 Mar 2012

## Slide 21
As of 8 Mar 2012

## Slide 23
Laverage(max)
(0.29 mb xsection)
Ions/bunch (max)
Past Week

## Slide 24
$ in BNL Balanced Billing Bank for FY12 (through Jan) = +$1,157K
$48/MWhr

## Slide 26
Run 12 Physics Stores to 28 Feb
Laverage(max)
(0.29 mb xsection)
Absolute scale should not be trusted)

## Slide 27
Store 16480 (27 Feb) – typical background issues
PHENIX
STAR
ZDC Singles
ZDC Singles
Protons/bunch
Protons/bunch
ZDC without and
with singles correction
ZDC without and
with singles correction

## Slide 28
Store 16480 (27 Feb) – typical background issues

## Slide 29
Store 16480 (27 Feb) – typical background issues

## Slide 30
Collision steering corrections background issues 26-27 Feb
ZDC Coincidence
ZDC Singles

## Slide 31
Lstore average(max)
Lpeak(max)
Example -- Store 16445, Sat Feb 18

## Slide 32
Blue Jet weighted average = 55.4 ± 0.5
Yellow Jet weighted average = 54.9 ± 0.5

## Slide 33
Run 12 projection for √s = 200 GeV pp
From Fischer et. Al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011
STAR Goal: 27 pb-1 delivered with 55-60 % polarization
PHENIX Goal: 27 pb-1 delivered with 55-60 % polarization
p2L = 8.2 pb-1 for 55% polarization

## Slide 34
First Physics Store (#16397, 04:01, 10 Feb)

## Slide 35
Today, 7 Feb 2012

## Slide 36
Typical Store from Run 9, 100 x 100 GeV pp

## Slide 37
Start cooldown
As of 16:18 hrs 20 Jan
3.5 days

## Slide 38
For Run 12 the PAC recommends the following (in order of priority):
5 weeks of running with polarized proton collisions at 200 GeV.
7 weeks of running with polarized proton collisions at 500 GeV.
5 weeks of running with Cu+Au collisions at 200 GeV.
3 weeks of running with U+U collisions at 193 GeV.
For Run13 the PAC recommends the following (not in order of priority):
12 weeks of running with polarized proton collisions at 500 GeV.
5 week of running with polarized proton collisions at 200 GeV.
7 weeks of running with Au+Au collisions at full energy.
Recommendations following the June 6-8, 2011 PAC

## Slide 39
D.L. November 23, 2011 update
Our helium supplier no longer able to meet our peek demand of 4 trailers in a one week period. They can give us one trailer a week starting on December 31st, so we expect to have all the helium we need, on time, but we will have to store most of it in the dewars outside 1006B. This will result in our 4K cooldown being a little less stable and predictable than it has been for the past few years when we received all of the helium at 1005R over a short period of time. Because of this, I expect the 4K cooldown will take a least one additional day.
Cryo Issue

## Slide 41
From Fischer et. al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011

## Slide 42
Run 12 projection for √s = 500 GeV pp
From Fischer et. Al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011

## Slide 43
Run 12 projection for √s = 193 GeV/n UU
From Fischer et. Al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011

## Slide 44
Run 12 projection for √s = 200 GeV/n CuAu
From Fischer et. Al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011