## Slide 1
Run 12 RHIC Machine/Experiments Meeting
21 Feb 2012
Agenda: open

## Slide 2: Run 12 Plan based on 20 weeks cryo operation –an example 20 week schedule based on Vincent’s pp start-up plan* Note physics weeks for 250 pp and HI are still to be determined
17 Jan, Begin cool-down to 4.5K
20 Jan, Cool-down to 4.5K in Blue and Yellow Ring complete, begin magnet setup
21-28 Jan, pp injection setup
28 Jan-3 Feb, LLRF, Ramp and store setup, begin 8 hr/night for experiments
3-10 Feb, 1 week ramp-up with 8 hrs/night for experiments
10 Feb, with store # 16397, begin 4 weeks pp physics with further ramp-up
16 Feb, 24/7 stores begin
9 March, end 4 week √s = 200 GeV pp run, begin ½ week setup for √s = 500 GeV pp
13 March, begin 1 week ramp-up to √s = 500 GeV with 8 hrs/night for experiments
20 March, begin 5 week pp physics run at √s = 500 GeV
24 April, end 5 week pp physics run at √s = 500 GeV
If Uranium or Cu-Au…
24 April, begin 1 week setup for UU or CuAu (no overnight stores for experiments)
1 May, begin 4.5 week UU or CuAu physics run
20-25 May: IPAC
2 June end 4.5 week UU or CuAu physics run
2 June, begin cryo warm-up
5 June, cryo warm-up complete (20.0 cryo-weeks)
Total Physics Weeks = 13.5
* http://www.cadops.bnl.gov/AGS/Operations/OpsWiki/index.php/RHIC_Setup:_Polarized_Protons

## Slide 3
With PHENIX = 0.25 mb; STAR = 0.235 mb (Run 9 xsections)

## Slide 4
Blue Jet weighted average = 57.8% ± 1.0; source blue average = 78.5%
Yellow Jet weighted average = 61.7% ± 1.0; source yellow average = 78.7%

## Slide 5
Run 12 Physics Stores to 21 Feb
Laverage(max)
Absolute scale should not be trusted)

## Slide 6
Lstore average(max)
Lpeak(max)
Example -- Store 16445, Sat Feb 18

## Slide 7
Other Slides

## Slide 8
Blue Jet weighted average = 55.4 ± 0.5
Yellow Jet weighted average = 54.9 ± 0.5

## Slide 9
As of 6 Feb 2012

## Slide 10
Run 12 projection for √s = 200 GeV pp
From Fischer et. Al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011
STAR Goal: 27 pb-1 delivered with 55-60 % polarization
PHENIX Goal: 27 pb-1 delivered with 55-60 % polarization
p2L = 8.2 pb-1 for 55% polarization

## Slide 11
As of 6 Feb 2012

## Slide 13
First Physics Store (#16397, 04:01, 10 Feb)

## Slide 14
Today, 7 Feb 2012

## Slide 15
Typical Store from Run 9, 100 x 100 GeV pp

## Slide 16
$ in BNL Balanced Billing Bank for FY12 (through Dec) = +$1,026K

## Slide 18
Start cooldown
As of 16:18 hrs 20 Jan
3.5 days

## Slide 20
For Run 12 the PAC recommends the following (in order of priority):
5 weeks of running with polarized proton collisions at 200 GeV.
7 weeks of running with polarized proton collisions at 500 GeV.
5 weeks of running with Cu+Au collisions at 200 GeV.
3 weeks of running with U+U collisions at 193 GeV.
For Run13 the PAC recommends the following (not in order of priority):
12 weeks of running with polarized proton collisions at 500 GeV.
5 week of running with polarized proton collisions at 200 GeV.
7 weeks of running with Au+Au collisions at full energy.
Recommendations following the June 6-8, 2011 PAC

## Slide 21
D.L. November 23, 2011 update
Our helium supplier no longer able to meet our peek demand of 4 trailers in a one week period. They can give us one trailer a week starting on December 31st, so we expect to have all the helium we need, on time, but we will have to store most of it in the dewars outside 1006B. This will result in our 4K cooldown being a little less stable and predictable than it has been for the past few years when we received all of the helium at 1005R over a short period of time. Because of this, I expect the 4K cooldown will take a least one additional day.
Cryo Issue

## Slide 24
From Fischer et. al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011

## Slide 25
Run 12 projection for √s = 500 GeV pp
From Fischer et. Al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011

## Slide 26
Run 12 projection for √s = 193 GeV/n UU
From Fischer et. Al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011

## Slide 27
Run 12 projection for √s = 200 GeV/n CuAu
From Fischer et. Al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011