## Slide 1
Run 12 RHIC Machine/Experiments Meeting
27 Mar 2012
Agenda:
Status reports
Other business

## Slide 2: Run 12 Plan based on 20 weeks cryo operation –an example 20 week schedule based on Vincent’s pp start-up plans* Note physics weeks for 250 pp and HI are still to be determined
17 Jan, Begin cool-down to 4.5K
20 Jan, Cool-down to 4.5K in Blue and Yellow Ring complete, begin magnet setup
21-28 Jan, pp injection setup
28 Jan-3 Feb, LLRF, Ramp and store setup, begin 8 hr/night for experiments
3-10 Feb, 1 week ramp-up with 8 hrs/night for experiments
10 Feb, with store # 16397, begin 4 weeks pp physics with further ramp-up
16 Feb, 24/7 stores begin
12 (Monday) March, end 4.4 weeks √s = 200 GeV pp, begin ½ week setup for √s = 510 GeV pp
16 March, begin 5 week pp physics (machine only) √s = 510 GeV
17/18 March, STAR/PHENIX physics start with longitudal polarization
Today – 27 March
23 April (Monday), end 5.4 week pp physics run at √s = 500 GeV
If Cu-Au and/or Uranium-Uranium…
23 April (Monday), begin 1 week setup for UU or CuAu (no overnight stores for experiments)
30 April, begin 4.7 week UU or CuAu physics run
20-25 May: IPAC
2 June end 4.7 week UU or CuAu physics run
2 June, begin cryo warm-up
5 June, cryo warm-up complete (20.0 cryo-weeks)
Total Physics Weeks = 14.5
* http://www.cadops.bnl.gov/AGS/Operations/OpsWiki/index.php/RHIC_Setup:_Polarized_Protons

## Slide 3
Thru fill 16626, 26 Mar

## Slide 4
Exp goals
w/50%pol
Thru fill 16626, 26 Mar
~35% of goal

## Slide 5
Blue weighted average = 50.8% ± 0.9%, 35% below source pol
Yellow weighted average = 50.4% ± 0.9%, 36% below source pol

## Slide 10
Table2: Max lumi parameters: 1.65x109/bunch, 0.6 b*, 20-25 mmmr emitt  peak = 200x1030 cm-2s-1
Average lumi goal
Peak lumi goal
Store 16632, 3/27/12

## Slide 11
$ in BNL Balanced Billing Bank for FY12 (through Feb) = +$1,825K
$30/MWhr

## Slide 12
As of 22 Mar 2012

## Slide 13
As of 22 Mar 2012

## Slide 16
Other Slides

## Slide 18
All “physics” stores beginning with16570, 15 March
~Lstore avg Goal

## Slide 19
16592
16578
16586
From “StoreAnalysis” program in “StartUp”
Polarization Goal

## Slide 20
STAR Goal for 5 weeks longitudal polarization (50% polarization):
  Sampled Luminosity = 45 pb-1 with 50% polarization
  Delivered Luminosity = 75 pb-1
PHENIX Goal for 5 weeks longitudal polarization (50% polarization):
  Sampled Luminosity = 30 pb-1 with |z| <30 cm
  = 10 pb-1 with |z| <10 cm
  Delivered Luminosity = 75 pb-1
Run 12, √s = 510 GeV polarized proton run – experiment goals

## Slide 21
Expectation for 5 weeks physics:
45-95 pb-1 delivered luminosity with 45-50% polarization
P4L ~ 4 pb-1

## Slide 22
STAR & PHENIX Goal

## Slide 23
Blue Jet weighted average = 61.2% ± 0.5%; source blue average = 77.5%  20% lost
Yellow Jet weighted average = 55.8% ± 0.5%; source yellow average = 77.4%  28% lost
STAR & PHENIX Polarization Goals
Offline polarization is larger

## Slide 25
Target (max projection)
Best stores, 16475 and 16534

## Slide 26
Best stores, 16475 and 16534

## Slide 27
Fill 16475, 27 Feb, 8.9 hours physics store (10 hour Lumi on Store), PHENIX 1.03 pb-1

## Slide 28
Fill 16475, 27 Feb, 8.9 hours physics store (10 hour Lumi on Store), PHENIX 1.03 pb-1
beginning
end

## Slide 29
Fill 16475, 27 Feb, 8.9 hours physics store (10 hour Lumi on Store), PHENIX 1.03 pb-1
beginning
end

## Slide 30
Fill 16534, 9 Mar, 8.1 hours physics store (9.1 hr Lumi on store), PHENIX 1.04 pb-1

## Slide 31
Fill 16534, 9 Mar, 8.1 hours physics store (9.1 hr Lumi on store), PHENIX 1.04 pb-1
Beginning
End

## Slide 32
Fill 16534, 9 Mar, 8.1 hours physics store (9.1 hr Lumi on store), PHENIX 1.04 pb-1
Beginning
End

## Slide 35
Laverage(max)
(0.29 mb xsection)
Ions/bunch (max)
Past Week

## Slide 37
Run 12 Physics Stores to 28 Feb
Laverage(max)
(0.29 mb xsection)
Absolute scale should not be trusted)

## Slide 38
Store 16480 (27 Feb) – typical background issues
PHENIX
STAR
ZDC Singles
ZDC Singles
Protons/bunch
Protons/bunch
ZDC without and
with singles correction
ZDC without and
with singles correction

## Slide 39
Store 16480 (27 Feb) – typical background issues

## Slide 40
Store 16480 (27 Feb) – typical background issues

## Slide 41
Collision steering corrections background issues 26-27 Feb
ZDC Coincidence
ZDC Singles

## Slide 42
Lstore average(max)
Lpeak(max)
Example -- Store 16445, Sat Feb 18

## Slide 43
Blue Jet weighted average = 55.4 ± 0.5
Yellow Jet weighted average = 54.9 ± 0.5

## Slide 44
Run 12 projection for √s = 200 GeV pp
From Fischer et. Al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011
STAR Goal: 27 pb-1 delivered with 55-60 % polarization
PHENIX Goal: 27 pb-1 delivered with 55-60 % polarization
p2L = 8.2 pb-1 for 55% polarization

## Slide 45
First Physics Store (#16397, 04:01, 10 Feb)

## Slide 46
Today, 7 Feb 2012

## Slide 47
Typical Store from Run 9, 100 x 100 GeV pp

## Slide 48
Start cooldown
As of 16:18 hrs 20 Jan
3.5 days

## Slide 49
For Run 12 the PAC recommends the following (in order of priority):
5 weeks of running with polarized proton collisions at 200 GeV.
7 weeks of running with polarized proton collisions at 500 GeV.
5 weeks of running with Cu+Au collisions at 200 GeV.
3 weeks of running with U+U collisions at 193 GeV.
For Run13 the PAC recommends the following (not in order of priority):
12 weeks of running with polarized proton collisions at 500 GeV.
5 week of running with polarized proton collisions at 200 GeV.
7 weeks of running with Au+Au collisions at full energy.
Recommendations following the June 6-8, 2011 PAC

## Slide 50
D.L. November 23, 2011 update
Our helium supplier no longer able to meet our peek demand of 4 trailers in a one week period. They can give us one trailer a week starting on December 31st, so we expect to have all the helium we need, on time, but we will have to store most of it in the dewars outside 1006B. This will result in our 4K cooldown being a little less stable and predictable than it has been for the past few years when we received all of the helium at 1005R over a short period of time. Because of this, I expect the 4K cooldown will take a least one additional day.
Cryo Issue

## Slide 52
From Fischer et. al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011

## Slide 53
Run 12 projection for √s = 500 GeV pp
From Fischer et. Al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011

## Slide 54
Run 12 projection for √s = 193 GeV/n UU
From Fischer et. Al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011

## Slide 55
Run 12 projection for √s = 200 GeV/n CuAu
From Fischer et. Al. “RHIC Collider Projections (FY 2012 – FY 2016)” 14 October 2011