## Slide 1
Run 13 RHIC Machine/Experiments Meeting
30 April 2013
Agenda:
Status Reports
Arguments for/against low energy Au run

## Slide 2: Run 13 plan based on 17 weeks cryo operation
11 Feb, Begin cool-down to 4.5K
15 Feb, Cool-down to 4.5K in Blue and Yellow Ring complete, begin magnet setup
26 Feb, first collisions
15 Feb -1 Mar, RHIC √s = 510 GeV pp machine setup
1-8 Mar, machine ramp-up with 8 hr/night for experiment setup
9 Mar (store 17201), begin √s = 510 GeV pp physics run today, 30 Apr…
decision time for switch to √s = 15 GeV/n AuAu.
if decide to run AuAu for 2.5 weeks (2 weeks physics)
20 May (Monday), switch to 15 GeV/n AuAu – begin ½ week AuAu setup
24 May (Friday), begin 15 GeV/n AuAu physics
7 June (Friday), end ~2.0 week √s = 15 GeV/n AuAu physics run or 13.0 week √s = 510 GeV pp physics run, begin cryo warm-up
10 June, cryo warm-up ~complete (17.0 cryo-weeks)

## Slide 3
Maximum goal
Maximum goal (peak lumi)
Run 12 lattice
PREVIOUS RECORD

## Slide 5
Preliminary, with Run 13 cross sections, singles corrected
PHENIX Goal, 250 pb-1 recorded, 750 pb-1 delivered, ≥ 55% polarization
STAR Goal, 165 pb-1 recorded, 275 pb-1 delivered, ≥ 55% polarization
Decision time for low energy AuAu
Preliminary, with Run 13 cross sections, PHENIX and STAR log based singles correction
Switch to low energy AuAu ??
17 cryo
weeks
Begin cryo
warm-up
(PHENIX Goal)
(STAR Goal)

## Slide 6
Preliminary, with Run 13 cross sections, PHENIX and STAR log based singles correction
Using average polarizations from CNI polarization from http://www.phy.bnl.gov/cnipol/fills/
750*(0.55)2
275*(0.55)2

## Slide 7
Preliminary, with Run 13 cross sections, PHENIX and STAR log based singles correction
Using average polarizations from CNI polarization from http://www.phy.bnl.gov/cnipol/fills/
750*(0.55)4
275*(0.55)4

## Slide 8
https://wiki.bnl.gov/rhicspin/Polarimetry/H-jet/Run13
Yellow average = 44.3 ± 0.8%
Blue average = 47.7 ± 0.7%
Average = 46.0%
stores 17201-17322 (eLens lattice)
Yellow average = 54.7 ± 0.6%
Blue average = 48.9± 0.5%
Average = 51.8%
stores 17328 – 17439 (Run 12 lattice)

## Slide 9
Yellow average = 52.5± 0.6%
Blue average = 53.4± 0.7%
Average = 53.0%
stores 17201-17322 (eLens lattice)
Yellow average = 55.0± 0.4%
Blue average = 54.3± 0.5%
Average = 54.7%
stores 17328-17434 (Run 12 lattice)

## Slide 11
+$1,086K in BNL bank through Mar 2013 (~$450K should come back to CAD)
Mar 2013 bill
$54.39 actual
billed at $53/Mwhr
March

## Slide 13
Additional Information

## Slide 14
Store 17391, 4/16/2013 – best peak lumi to date
Lpeak(maximum=2.7x1032)
Laverage(maximum=1.6x1032)
Ions (maximum)
Lpeak(= 2.1x1032 cm-2s-1

## Slide 15
Goal emittance (19-25 p mm-mr)

## Slide 16: Run 13 plan based on 20 weeks cryo operation and Fischer et.al. RHIC Collider Projections (FY 2013 – FY 2017), 27 Sep 2012
11 Feb, Begin cool-down to 4.5K
15 Feb, Cool-down to 4.5K in Blue and Yellow Ring complete, begin magnet setup
26 Feb, first collisions
15 Feb -1 Mar, RHIC √s = 510 GeV pp machine setup
1-8 Mar, machine ramp-up with 8 hr/night for experiment setup
9 Mar (store 17201), begin √s = 510 GeV pp physics run today, 23 Apr…
27 May, end 15 cryo weeks
6 Jun, switch to √s = 15 GeV/n AuAu if pp goals are met and end 12.7 week √s = 510 GeV pp physics run
27 Jun, end ~2.5 week √s = 15 GeV/n AuAu physics run or 15.9 week √s = 510 GeV pp physics run, begin cryo warm-up
30 June, cryo warm-up ~complete (19.9 cryo-weeks)
See http://www.rhichome.bnl.gov/AP/Spin2013/ for the Run Coordinator’s detailed plan

## Slide 17
Preliminary, with Run 13 cross sections, PHENIX and STAR log based singles correction

## Slide 18
Preliminary, with Run 13 cross sections, singles corrected
PHENIX Goal, 250 pb-1 recorded, 750 pb-1 delivered, ≥ 55% polarization
STAR Goal, 165 pb-1 recorded, 275 pb-1 delivered, ≥ 55% polarization
PHENIX GOAL
STAR GOAL
Decision time for low energy AuAu
15 cryo weeks
Preliminary, with Run 13 cross sections, PHENIX and STAR log based singles correction
Switch to low energy AuAu ??
17 cryo weeks
19.9 cryo weeks

## Slide 19
Example Store for STAR (17340) with “physics” time cuts
Log based singles correction  8.48E8/2.8mb = 3.03 pb-1
Standard singles correction  6.371E8/2.5mb = 2.55 pb-1
Integrated lumi Log/Standard = 1.19
ZDC Standard singles corr.
ZDC Log singles corr.
Raw ZDC coinc
integrals
}
~x1.2
(1.1 lumi)
~x1.5
(1.3 lumi)

## Slide 20
Ions (maximum)
Past 2 Weeks
Physics stores
Lpeak(maximum=2.7E32)
Using Run 13 cross sections with log based singles correction
Laverage(maximum)
Run 12 lattice
17340

## Slide 21
Run 12 lattice

## Slide 22
Yellow average = 48.12± 0.4%
Blue average = 53.1 ± 0.5%
http://www.phy.bnl.gov/cnipol/fills/

## Slide 23
http://www.phy.bnl.gov/cnipol/fills/
Yellow average = 57.7± 0.4%
Blue average = 55.9 ± 0.4%
Average = 56.8%

## Slide 24
Blue jet target weighted average = 50.3% ± 0.5%
Yellow jet target weighted average = 53.4% ± 0.5%
And Yellow beam at injection jet target Run 12 result = 63.0 ± 4.4%

## Slide 25
Yellow average = 53.4 ± 0.5%
Blue average = 50.3 ± 0.5%

## Slide 32
For Run 13 the PAC recommends the following (in order of priority):
Running with polarized proton collisions at 500 GeV to provide an integrated luminosity of 750 pb-1 at an average polarization of 55%.
2. Depending on the amount of running time remaining after priority #1
  a. If less than 3 weeks remain, a week of 200 GeV Au+Au collisions.
  b. If at least 3 weeks of running time remain, 3 weeks of 15 GeV Au+Au
  collisions.
3. 8 days of 62 GeV p+p collisions.
4. At the discretion of the ALD, 4 days of low-luminosity running to accomplish the pp2pp goals.