## Slide 1
Run 13 RHIC Machine/Experiments Meeting
21 May 2013
Agenda:
Status Reports

## Slide 2: Run 13 plan based on 17 weeks cryo operation
11 Feb, Begin cool-down to 4.5K
15 Feb, Cool-down to 4.5K in Blue and Yellow Ring complete, begin magnet setup
26 Feb, first collisions
15 Feb -1 Mar, RHIC √s = 510 GeV pp machine setup
1-8 Mar, machine ramp-up with 8 hr/night for experiment setup
9 Mar (store 17201), begin √s = 510 GeV pp physics run
5 April, reverted to Run 12 lattice today, 21 May
10 June (Monday, 0800), end 13.4 week √s = 510 GeV pp physics run, begin cryo warm-up
13 June, cryo warm-up ~complete (17.4 cryo-weeks)

## Slide 3
Maximum goal
Maximum goal (peak lumi)
Maximum goal (average lumi)

## Slide 5
Preliminary, with Run 13 cross sections, singles corrected
PHENIX Goal, 250 pb-1 recorded, 750 pb-1 delivered, ≥ 55% polarization
STAR Goal, 165 pb-1 recorded, 275 pb-1 delivered, ≥ 55% polarization
Preliminary, with Run 13 cross sections, PHENIX and STAR log based singles correction
17.4 cryo
weeks
Begin cryo
warm-up
(PHENIX Goal)
(STAR Goal)

## Slide 6
https://wiki.bnl.gov/rhicspin/Polarimetry/H-jet/Run13
Yellow average = 44.3 ± 0.8%
Blue average = 47.7 ± 0.7%
Average = 46.0%
stores 17201-17322 (eLens lattice)
Yellow average = 54.4± 0.4%
Blue average = 49.7 ± 0.4%
Average = 52.1%
stores 17328 – 17530 (Run 12 lattice)
Average for all fills: Blue = 49.3% +/- 0.3%, Yellow = 52.4% +/- 0.4%

## Slide 7
Yellow average = 52.7± 0.5%
Blue average = 53.3± 0.5%
Average = 53.0%
stores 17201-17322 (eLens lattice)
Yellow average = 55.7± 0.3%
Blue average = 54.3± 0.4%
Average = 55.0%
stores 17328-17530 (Run 12 lattice)
Average for all fills: Blue = 53.9% +/- 0.3%, Yellow = 54.8% +/- 0.3%

## Slide 9
Preliminary, with Run 13 cross sections, PHENIX and STAR log based singles correction
Using average polarizations from CNI polarization from http://www.phy.bnl.gov/cnipol/fills/
750*(0.55)2
275*(0.55)2

## Slide 10
Preliminary, with Run 13 cross sections, PHENIX and STAR log based singles correction
Using average polarizations from CNI polarization from http://www.phy.bnl.gov/cnipol/fills/
750*(0.55)4
275*(0.55)4

## Slide 11
Additional Information

## Slide 12
Unresolved issue…
STAR Lumi has been above PHENIX since the STAR crossing angle was fixed
around mid-April
??

## Slide 17
+$1,086K in BNL bank through Mar 2013 (~$450K should come back to CAD)
Mar 2013 bill
$54.39 actual
billed at $53/Mwhr
March

## Slide 20
Store 17391, 4/16/2013 – best peak lumi to date
Lpeak(maximum=2.7x1032)
Laverage(maximum=1.6x1032)
Ions (maximum)
Lpeak(= 2.1x1032 cm-2s-1

## Slide 21
Goal emittance (19-25 p mm-mr)

## Slide 22: Run 13 plan based on 20 weeks cryo operation and Fischer et.al. RHIC Collider Projections (FY 2013 – FY 2017), 27 Sep 2012
11 Feb, Begin cool-down to 4.5K
15 Feb, Cool-down to 4.5K in Blue and Yellow Ring complete, begin magnet setup
26 Feb, first collisions
15 Feb -1 Mar, RHIC √s = 510 GeV pp machine setup
1-8 Mar, machine ramp-up with 8 hr/night for experiment setup
9 Mar (store 17201), begin √s = 510 GeV pp physics run today, 23 Apr…
27 May, end 15 cryo weeks
6 Jun, switch to √s = 15 GeV/n AuAu if pp goals are met and end 12.7 week √s = 510 GeV pp physics run
27 Jun, end ~2.5 week √s = 15 GeV/n AuAu physics run or 15.9 week √s = 510 GeV pp physics run, begin cryo warm-up
30 June, cryo warm-up ~complete (19.9 cryo-weeks)
See http://www.rhichome.bnl.gov/AP/Spin2013/ for the Run Coordinator’s detailed plan

## Slide 23
Preliminary, with Run 13 cross sections, PHENIX and STAR log based singles correction

## Slide 24
Preliminary, with Run 13 cross sections, singles corrected
PHENIX Goal, 250 pb-1 recorded, 750 pb-1 delivered, ≥ 55% polarization
STAR Goal, 165 pb-1 recorded, 275 pb-1 delivered, ≥ 55% polarization
PHENIX GOAL
STAR GOAL
Decision time for low energy AuAu
15 cryo weeks
Preliminary, with Run 13 cross sections, PHENIX and STAR log based singles correction
Switch to low energy AuAu ??
17 cryo weeks
19.9 cryo weeks

## Slide 25
Example Store for STAR (17340) with “physics” time cuts
Log based singles correction  8.48E8/2.8mb = 3.03 pb-1
Standard singles correction  6.371E8/2.5mb = 2.55 pb-1
Integrated lumi Log/Standard = 1.19
ZDC Standard singles corr.
ZDC Log singles corr.
Raw ZDC coinc
integrals
}
~x1.2
(1.1 lumi)
~x1.5
(1.3 lumi)

## Slide 26
Ions (maximum)
Past 2 Weeks
Physics stores
Lpeak(maximum=2.7E32)
Using Run 13 cross sections with log based singles correction
Laverage(maximum)
Run 12 lattice
17340

## Slide 27
Run 12 lattice

## Slide 28
Yellow average = 48.12± 0.4%
Blue average = 53.1 ± 0.5%
http://www.phy.bnl.gov/cnipol/fills/

## Slide 29
http://www.phy.bnl.gov/cnipol/fills/
Yellow average = 57.7± 0.4%
Blue average = 55.9 ± 0.4%
Average = 56.8%

## Slide 30
Blue jet target weighted average = 50.3% ± 0.5%
Yellow jet target weighted average = 53.4% ± 0.5%
And Yellow beam at injection jet target Run 12 result = 63.0 ± 4.4%

## Slide 31
Yellow average = 53.4 ± 0.5%
Blue average = 50.3 ± 0.5%

## Slide 33
For Run 13 the PAC recommends the following (in order of priority):
Running with polarized proton collisions at 500 GeV to provide an integrated luminosity of 750 pb-1 at an average polarization of 55%.
2. Depending on the amount of running time remaining after priority #1
  a. If less than 3 weeks remain, a week of 200 GeV Au+Au collisions.
  b. If at least 3 weeks of running time remain, 3 weeks of 15 GeV Au+Au
  collisions.
3. 8 days of 62 GeV p+p collisions.
4. At the discretion of the ALD, 4 days of low-luminosity running to accomplish the pp2pp goals.