## Slide 1: Run 2020

## Slide 2: Scheduling Physicist: Robert Pak
e-mail: pak@bnl.gov
Office Phone: (631) 344-4380

## Slide 3: Run20 Planned Schedule

## Slide 4
Run20 Final Schedule

## Slide 5: Run 2020 Schedule
Blue cooldown begins: 11/04/2019
Yellow cooldown begins: 11/04/2019
Blue 4K reached: 12/03/2019
First circulating bunch (Au) in Blue: 12/05/2019
Yellow 4K reached: 12/06/2019
First circulating bunch in Yellow (Au):12/07/2019
LEReC Running Start: 12/12/2019
Physics Start for 197Au79+ on 197Au79+: 12/10/2019
Fixed Target 197Au79+ Start: 01/27/2019
End Physics Operations: 03/20/2019
Suspension of RHIC and LEReC activities: 03/20/2019
Resumption of RHIC activities: 06/15/2020
Begin Cryo Warmup: 09/15/2020
Cryo Warmup Complete: 09/18/2020

## Slide 6: Mode Schedule
Mode 1A: 197Au79+ on 197Au79+ at 5.75GeV/nucleon
  Beam operation: 12/05/2019 - 02/24/2020
Mode 1B: 197Au79+ on 197Au79+ at 4.59GeV/nucleon
  Beam operation: 12/16/2020-03/20/2020
  Beam operation cont.:06/15/2020-09/01/2020
Mode 1C: 197Au79+ at 31.2GeV/nucleon on fixed target 197Au foil
  Beam operation: 01/27/2020 - 01/29/2020
Mode 1D: 197Au79+ at 9.8GeV/nucleon on fixed target 197Au foil
  Beam operation: 01/29/2020 - 02/01/2020
Mode 1E: 197Au79+ at 19.5GeV/nucleon on fixed target 197Au foil
  Beam operation: 02/01/2020 - 02/02/2020
Mode 1F: 197Au79+ at 13.5GeV/nucleon on fixed target 197Au foil
  Beam operation: 02/02/2020 - 02/03/2020
Mode 1G: 197Au79+ at 7.3GeV/nucleon on fixed target 197Au foil
  Beam operation: 02/03/2020 - 02/05/2020
Mode 1H: 197Au79+ at 5.75GeV/nucleon on fixed target 197Au foil
  Beam operation: 02/13/2020 - 02/14/2020
Mode 1I: LEReC cooling commissioning with 197Au79+ 3.85GeV/nucleon
  Beam operation: 09/01/2020-09/07/2020
Mode 1J: 197Au79+ in Yellow ring for CeC PoP at 26.5GeV/nucleon particle energy
  Beam operation: 03/11/2020-09/14/2020

## Slide 7: Run Coordinators
Chuyu Liu [RHIC and STAR Operations]
  Email: cliu1@bnl.gov
  Office Phone: (631) 344-4431
  Modes: 1A, 1B, 1C, 1D, 1E, 1F, 1G, 1H
Vladimir Litvinenko [CeC Operations]
  Email: vl@bnl.gov
  Office Phone: (631) 344-2570
  Modes: 1J
Igor Pinayev [CeC Operations]
  Email: pinayev@bnl.gov
  Office Phone: (631) 344-5706
  Modes: 1J

## Slide 8: Run Overview

## Slide 9: Basic Run Parameters
Mode Name | Energy/ Nucleon [GeV] | No. Bunches | Ions/ bunch [109] | Β* [m] | rms emittance [μm] | Peak Luminosity [cm-2s-1] | Average Luminosity [cm-2s-1] | STAR Luminosity [μb-1]
1A | 5.75 | 111 | 1.3 | 4 | 2.0 | 90×1024 | 50×1024 | 143
1B | 4.59 | 111 | 1.2 | 4.53.53.0 | 1.5 | 48×1024 | 35.5×1024 | 176
1C | 31.2 | 12 | 1.5 | 5 | 33 |  |  | 23
1D | 9.8 | 12 | 1.25 | 10 | 22 |  |  | 23
1E | 19.5 | 12 | 1 | 10 | 1.5 |  |  | 25
1F | 13.5 | 12 | 1 | 10 | 2.41.8 |  |  | 21
1G | 7.3 | 12 | 1 | 10 | 1.4 |  |  | 24
1H | 5.75 | 12 | 1 | 10 | 21.5 |  |  | 24
1I | 3.85 | 111 | 0.8 | 4.53.0 | 1.50.5 | 44×1024 | 19×1024 | 

## Slide 11: Percentage of Time per Mode Run20

## Slide 12: LEReC Cooling

## Slide 13
Image courtesy of A. Fedotov

## Slide 14: Event rate comparison cooling vs no cooling for 4.59 GeVores.

## Slide 15: Luminosity for 197Au79+ on 197Au79+ Physics

## Slide 22: 197Au79+ Physics on Fixed Target 197Au foil

## Slide 23: Basic Fixed Target Numbers
Energy/Nucleon | Time in Physics [Hrs] | Total Events
31.2 GeV | 25.5 | 112M
19.5 GeV | 34.5 | 108M
13.5 GeV | 24.25 | 118M
9.8 GeV | 34.5 | 108M
7.3 GeV | 27 | 117M
5.75 GeV | 22.5 | 116M

## Slide 26
F

## Slide 30: Power and Cryo Use
Power consumption data shown through 2020

## Slide 31: Cryo Cooldown
29.0 Cryo Weeks for physics
12.4 Cryo Weeks with no ops

## Slide 37: Useful Websites
Machine/Detector Planning Page
  http://server.c-ad.bnl.gov/esfd/RMEM_20/rhic_planning.htm
RHIC Run Overview (FY01-FY20)
  https://www.rhichome.bnl.gov/RHIC/Runs/index.html#Run-20
RHIC Retreat Page (FY20)
  https://indico.bnl.gov/event/9276/
Store Statistics
  https://www.agsrhichome.bnl.gov/AGS/Operations/Run20/
Scheduling Physicist
  https://www.c-ad.bnl.gov/esfd/Scheduling_Physicist/FY20_Collider-Accelerator_Schedule.htm