## Slide 1
Run 22 RHIC Machine/Experiments Meeting
December 7, 2021
Agenda:
Welcome and Overall schedule for the FY 22 RHIC run - W. Christie
STAR status, schedule, and update - J.H. Lee
CeC status, schedule, and update - I. Pinayev
RHIC status, schedule, and update - V. Schoefer
All Other Business (AOB)

## Slide 2
SD1
Rough Look at Long Term Schedule
2021 Run (24 wks) 1/25 – 7/12 |  |  |  |  | 
2021 |  |  |  |  |  |  |  |  |  |  |  | 2022 |  |  |  |  |  |  |  |  |  |  |  | 2023 | 
J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F
2022 Run (20 wks) 11/15 – 4/4 |  |  |  | 
SD2 (18 wks) 7/12 – 11/15 |  |  |  | 
sPHENIX1 (16) 4/4 – 7/25 |  |  | 
sPHENIX2 (17 wk) 7/25 – 11/23 |  |  |  | 
sPHENIX3 (67 D) 11/24 – 1/30 |  | 
2023
Run
N.B. Whereas STAR was asked to submit a BUR for the 2021 run for 24 and 28 Cryo weeks, the baseline schedule above assumes 24 weeks for the 2021 run.
N.B. This Schedule was the result of meetings that were held in late summer of 2020 to discuss the longer-term schedule.

## Slide 3
A calendar for the remainder of Calendar 2021
Today’s date
Scheduled start of Helium cooldown. With schedule issue that arose three weeks ago, the cooldown started for only the Blue ring.
Yellow ring cooldown started.
First collisions for STAR.
Discussion topic: With today’s news about the broken Blue ring snake magnet discuss near term strategy and plans. Key question is polarization that can be achieved for Blue beam.

## Slide 4
All Other Business (AOB)
AOB

## Slide 5
Program Advisory Committee (PAC) recommendations on the 2022 RHIC Run
2.2 Discussion and Recommendations for RHIC Run 22
The Run 22 BUR of a transversely polarized pp run at 510 GeV with the STAR Forward Upgrade represents a unique opportunity to address important issues in spin physics and will allow exploration of the regimes of low and high-x physics with unprecedented precision. New results anticipated for Run 22 with the Forward Upgrade can have important impacts on the planning for EIC, as well as on the interpretation of EIC data. The PAC strongly endorses the STAR Run 22 BUR.
.
.
.
If Run 22 were to be reduced from 20 to 18 weeks that would result in at least a 15% reduction of the integrated luminosity and have a very detrimental effect on the prospects of achieving all the physics goals. Given that the CeC beam time would additionally reduce the STAR run by 2.6 weeks, this would have further negative effects on the physics programme. C-AD is strongly encouraged to optimize RHIC operations to fulfill the goals of both CeC and STAR.
What is shown here are the first and eighth paragraphs from the PAC report concerning the 2022 RHIC run. The other paragraphs of the section deal with physics, as opposed to operations topics.