## Slide 1: Preparations for RHIC Heavy Ion Run-11
Gregory Marr
Run website: http://www.cadops.bnl.gov/AP/RHIC2011/
http://www.rhichome.bnl.gov/AP/RHIC2011/

## Slide 2: EBIS milestones
See C. Gardner’s commissioning plan for details on FY10 results.
  http://www.cadops.bnl.gov/AGS/Operations/GardnerNotes/EbisNotes/ETBplan10.pdf
Ensure Tandem beams are unaffected by large ETB bend.
  Tests complete prior to Run-11
Re-establish EBIS beam in Booster.
  He, Ne, Fe, Au all accelerated in Booster.
  Ar, Ti, O development for NSRL.
  Development of U beams yet to come.
Ensure two EBIS beams can operate concurrently.
  Multiple source development yet to come.
  May or may not be required this run.
Establish required intensities for present & future operations.
  Fe: established near present Tandem intensities for NSRL.
    Required for concurrent RHIC-Au/NSRL-Fe operations.
  Au: at or above present Tandem intensities for RHIC.
  U: 70% of present Au intensities in AGS.

## Slide 3: Upgrades impacting Heavy Ions
197 MHz Storage cavity relocation
  Eliminating “common cavities” should improve beam loading issues associated with rebucketing.
Stochastic cooling
  Vertical and longitudinal, no horizontal.

## Slide 4: Lattice Development
9 GeV: “Au11v0”
  2.5 m β* at STAR
  3m β* at PHENIX
  6m β* at AnDY
  10m β* elsewhere
  Nominal injection tunes (28.22, 29.23)
100 GeV
  TBD

## Slide 5: Projections
9 Gev Au
  111 bunches
  ≥1e9/bunch
  ≥ 20 min lifetime (Satogata C-A/AP 360), ~1 hour stores?
  Fill time ≤ 10 min
100 GeV Au
  See plot on website

## Slide 6: Schedule and Run Plan
Preliminary Schedule:
  Saturday, 4/2: Injector setup begins
  Friday, 4/8: Polarized run ends
  Friday, 4/8: RHIC beam development begins
    18 GeV Au-Au
      ~ 3 days Start Up mode
      ~ 3 days Ramp Up mode
  Friday, 4/15: Physics begins

## Slide 7: Schedule and Run Plan
Scheduling conflicts:
  APEX/MD vs. injector setup, Wed 4/6
  NSRL Ti vs. RHIC setup, Sat 4/9
    Not an issue if EBIS/Booster Titanium setup completes.
  NSRL O vs. RHIC setup, Tue 4/12
    Not an issue if EBIS/Booster Oxygen setup completes.

## Slide 8: Present Status
Tandem providing Au 31+ to Booster
Beam accelerated to full energy in Booster
Awaiting clearance for AGS, ATR, RHIC…