## Slide 1: Maintenance and Accelerator Support
RHIC Start Up 12

## Slide 2: Accelerator Status:
EBIS, LINAC, Booster and AGS are presently setting up with beam.
  Access to AGS and Booster scheduled around failure.
  Submit desired jobs to the job request system.
AGS extraction setup in progress.
  No Access to U downstream, W, X and Y lines.
  Any access to be scheduled.
Maintenance Tomorrow.

## Slide 3: RHIC status:
Tunnel and IRs on Restricted Access.
Shielding in place, awaiting inspection.
No Access, eves and nights starting January 20th.
Presently ODH1 in the tunnel.
Berm areas of RHIC are secured, scheduled access only.
4k wave started on time today.

## Slide 4: This week:
Controlled/Radiation area postings at RHIC, ring road.
Wednesday – Saturday (Following 4k wave):
  Secure any normally locked/fenced areas as necessary.
  Power supply and Cryogenic work during the day/evening.
  Beam work evenings/nights starting 1/21
  Select areas of the ring secured during the daytime. Schedule for securing TBD.
When RHIC is ready for beam, secure experimental areas

## Slide 5: During the Ramp Up.
Injectors will remain closed and running with beam.
Any RHIC access will be scheduled at daily meetings.
Daily schedules will be published on the Web and displayed on the CATV system.
E-lens Phase shifter tests will occur after power supply checkout is complete.

## Slide 6: Tomorrow's Maintenance
LINAC tube replacement.
  Mod 6 (BLIP remains on).
Booster off from 0600-1200hrs
  Access from 0700-1100hrs.
  OPPIS source maintenance.
AGS off from 0600-1400hrs.
  RF maintenance and repair.
Scheduling here 1430hrs.