## Slide 1: RHIC Status Update
Time Meeting, V. Schoefer
1/24/12
Progress of beam work
  Four scheduled shifts with beam so far
    Established captured beam with good lifetime (snakes on) and the bulk of instrumentation setup in the first three
    Lost the last of the four to 9 MHz failure
Power supply progress
  Blue delivered for injection 1 day early (Thanks, Don and co.!)
  Yellow ready for injection tonight
  Blue through 100 GeV hysteresis by tonight
  Still planning on finishing p.s. work on 1/28.
RF work
  Blue capture on new LLFR took 1 shift (as estimated, Thanks Alex and Kevin and co.!)

## Slide 2
Time Meeting, V. Schoefer
1/24/12
To be done this week
  At injection
    Repeat the above with yellow
    Finish instrumentation setup in blue
      Orbit feedback tests
      10 Hz feedback tests
      BPMs to fixed trigger
    CNI setup in both rings
  Prepare for ramping
    Finish power supply work (inluding DX training)
    Setup and commissioning of new LLRF loops
  Begin 100 GeV ramp development
RHIC Status Update