## Slide 1: Maintenance and Accelerator Support
RHIC Start Up 12

## Slide 2: Accelerator Status:
All Machines are normally in No Access Mode and running for Setup.
RHIC:
  Access determined at daily 0900hrs meeting
  Scheduled maintenance follows Physics- Feb 15th tentative 1st MD.
  Submit Access requests to the Job Request or Ring Access request systems.

## Slide 3: Last Week
Wednesday:
  OPPIS maintenance was completed - planned accesses and maintenance work postponed.
Thursday:
  Some Maintenance items completed- AGS C15 polarimeter, Siemens

## Slide 4: This week:
Today and tomorrow:
  No Scheduled Access- setup continues…
Thursday:
  PHENIX detector work 0900-1300hrs
  E-lens phase shifter thigh current tests 0900-1500hrs- NO TUNNEL ACCESS PERMITTED

## Slide 5: Maintenance Next Wednesday:
Submit all desired jobs as early as possible.
Major works discussed at Supervisors Meeting Thursday (9am Snyder)
Approval confirmation by auto-email.
Draft schedule this Friday afternoon.
Final schedule after Scheduling Meeting next Tuesday.