## Slide 1: Maintenance and Accelerator Support
RHIC Run 12

## Slide 2: RHIC species change completed:
Major works in RHIC:
  Power supply reconfigure (DO polarity at 6 and 8 o’clock).
  Ramp setup and commissioning.
  PHENIX drift chamber repair.
  RF repair.
  E-lens feed through.
  Stochastic cooling work.

## Slide 3: Maintenance Tomorrow
Installation and commissioning at a minimum.
Maintenance items for RHIC to be completed in ~4 hours.
AGS access for RF repair and maintenance 0800-1000hrs
LINAC and Booster to run for NSRL and BLIP (1 hour interruption to BLIP in the morning)..
Complete details discussed here at 1430hrs today.

## Slide 4: Schedule in Brief
Time | Activity | Personnel
0001-0700 | Fill RHIC as needed for 0900hrs dump | MCR
0700 | AGS equipment off, LINAC and Booster remain on. Set up for NSRL proton running as necessary. Apply AGS LOTO. | MCR MCR CAS
0800 | Access AGS for RF and ACS work only. LINAC off for solenoid work | CAS/HP/MCR
0900 | Dump the RHIC beams and begin tunnel access. Select areas to RA, Access 10 o’clock dump areas for surveys | CAS/MCR MSG/MCR
1000 | Secure AGS, remove LOTO | 
1100 | Restore AGS systems. NSRL experimental setup. | MSG NSRL
1200 | NRSL running for users. | MCR/NSRL
1300 | Begin RHIC sweeps. | CAS/MCR
1400 | Sweep experimental areas. | CAS/MCR
1500 | Begin Physics restoration. | AP/MCR