Building 911-B

P.O. Box 5000

Upton, NY 11973-5000

Phone 631 344-6102

Fax 631 344-5954

sivertz@bnl.gov

managed by Brookhaven Science Associates
for the U.S. Department of Energy

Memo

Date:		13 November 2007

From:		M. Sivertz

To:		J. Benante, D. Bruno, W. Christie, A. Drees, G. Ganetis, C. Gardner,

J.W. Glenn, M. Mapes, P. Ingrassia, Y. Makdisi, I. Marneris,

C. Montag, E. O'Brien, C. Pearson, A. Pendzick, F Pilat, A. Rusek, T. Russo,

J. Sandberg, P. Sampson, J. Tuozzolo, R. Zaharatos, A. Zaltsman, A. Zhang

cc:		D. Barton, W. Fischer, R. Karol, D. Lowenstein, P. Pile, T. Roser

## Subject:	Derived from Minutes of Meeting on Maintenance Policy for RHIC Run 7

Attending: J. Benante, W. Christie, C. Gardner, J. Haggerty, P. Ingrassia, Y. Makdisi, E. O'Brien, C. Pearson, A. Pendzick, F Pilat, J. Sandberg, P. Sampson, J. Tuozzolo, R. Zaharatos, A. Zaltsman

# The committee met on Wednesday September 13 to discuss and define plans for scheduled maintenance for Run-7, as a follow-up from discussions on maintenance at the RHIC Retreat in July 2007.

The following maintenance policy was developed by Fulvia Pilat at a meeting on 13 September 2006, and has been modified to reflect the 2008 schedule.

Maintenance Day Schedule

- While developing colliding beam, there will be no scheduled maintenance days.

- The first scheduled maintenance day will be 28 November 2007.

- Maintenance Days will occur every Wednesday after that during the period of tuning up intensity and the experimental shake down period, from 28 November through 19 December 2007.

- During routine Physics running starting 19 December 2007, Maintenance Days will occur every two weeks on Wednesdays.

Maintenance Day Protocol

- The standard duration for Maintenance Day work will be 8 hours.

  - This translates into a minimum of 12 hours down time with beginning and end effects.

- The default start time for injectors requiring LOTO prior to entry will be 6:00AM

  - The goal is to have the machines available for access by workers at 8:00AM sharp. (This impacts the physics program and APEX, as refilling will not be available between 6:00AM and 8:00AM the day of maintenance).

- RHIC start work time is 8:00AM

- Operational testing shall remain part of each job.

  - Time for these tests shall be included in the job request.

- Recovery periods will be an explicit part of the Maintenance Day Schedule and occur as soon as machines become available.

- Access will be done on Controlled Access when possible to minimize the need for sweeps and additional LOTO.

- Technicians from STAR and PHENIX should be trained for active roles in the experiments sweeps. That will free personnel for other maintenance and recovery activity.

- CAD, STAR and PHENIX will generate a list of installation and upgrade work for systems and detectors – other than repairs and preventive maintenance - that are planned for Maintenance Days during Run-8. To have an overall list upfront should allow better planning, as it was discussed at the Retreat.  In the event of a delayed start of the run, the lists may change and needs to be kept up to date.

- The issue of Booster maintenance when both NSRL and RHIC are running was brought up and discussed. That consideration should be part of the scheduling of the next NSRL run in spring 08.

These issues may of course be revisited if plans for the run or other circumstances change.