## Slide 1
RHIC Run 22 Run Status 3/15/2022, V. Schoefer
Switch to Siemens, from Westinghouse was extremely smooth: no RHIC downtime
  Polarization immediately after switch comparable to WH
  With jump quads:
    Polarization in both rings ~55% at store
Recent yellow sextupole trips (y09-sxd2)affecting both luminosity and polarization (via beam loss and emittance growth)
STAR magnet trips due to power distribution problem: multi-hour downtime
  Plan to address behind APEX tomorrow
RHIC pC [%]
STAR ZDC [Hz]
RHIC Intensity [1e11]
y. Dump kciker
Jump quads on w/ Siemens
Siemens->
STAR magnet
STAR magnet/weather
Q. Det/Y. Sext
Y. Sext trips

## Slide 2
RHIC Emittance
RHIC emittance consistently low for fills in Siemens
  More apparent at injection than store

## Slide 3
RHIC Polarization
Benefit of the Siemens from both higher average and more consistent polarization
Jet pol
Jet avgs since Siemens switch: (B,Y) = 55,54%
Jet avgs on Westinghouse: (B.Y) = 49,48%

## Slide 4: Run extension
New run end data Apr 18th (instead of Apr 4th)
Previous schedule: Apr 4th end, 4 days of CeC 16 remaining days for physics
Extension schedule: Apr 18th end, 12 days of CeC  22 remaining days for physics
Two week extension is a 6 day extension for the RHIC colliding beam physics program – Not enough to substantially alter plans for the remainder of the run.

## Slide 5: Projections for delivered Figure of Merit
Delivered FOM target = 180 pb-1
April 6th
April 18
Delivered target based on 120 pb-1 sampled target and factor of 0.7 between delivered and sampled (as defined by CAD and STAR respectively)
Fit projection based on last 2 weeks which includes: one week on Westinghouse with 2 full days of failure and last week on Siemens with no interruptions for APEX/Maintenance/Development
  (Difficult to project when there are no normal weeks!)
April 18th is nominal end, April 6th is nominal end minus 12 days
Goal is barely achievable in the remaining time
  Two week projection is extremely imprecise
  Become likelier if the cross section is < 2.09 mb

## Slide 6: Plans for the week
Characterize stable spin direction at the pC polarimeter
  Create largest allowable orbital angle at local of pC target (limited by aperture)
  Scan angle and measure spin direction
  Infer longitudinal component from projections with additional precession