## Slide 1
RHIC/Experiments Coordination Meeting: Run 22, 11/16/2021
Setup Status
Review of (an) improvement relative to Run 17
  Why?
Startup plan modifications with the delay

## Slide 2: Status
RHIC cooldown started Mon 11/15
  Full cooldown delays first beam to ~12/5 (for cryo work)
AGS setup paused for BtA obstruction remediation
  Replacement of valve piece with bellows with nitrogen scrubbing and partial bake to hopefully avoid a full bakeout (Fri 11/19 eve—Mon 11/22 morning).
  Resumption of AGS setup Monday if pressure checks out.
  Leaves 2 calendar weeks for AGS setup.

## Slide 3: Two bunches in AGS from Run 13
3
Polarization
Emittance (95%,norm)
Intensity
H=1
H=2
Data from H. Huang
In Run 13, proton bunches were captured on h=2 at Booster injection and accelerated to AGS extraction as two bunches as a test
Improvement at the time
20% emittance improvement
12% (relative) polarization improvement
  Center-measured in AGS
The proposed scheme splits in the Booster instead of h=2 capture to preserve dual harmonic capture (which gives lower peak currents at Booster injection)

## Slide 4: Bunch split and merge scheme
Present scheme: Single bunch from source to RHIC, dual harmonic RF at Booster and AGS injection
Extract to AGS
Extract to RHIC
Dual harmonic RF (h=1,2,adiabatic capture)
Dual harmonic RF (h=6,12)
Booster
AGS
Extract to AGS
Extract to RHIC
AGS
Dual harmonic RF
Booster
Proposed scheme: Add a longitudinal split in Booster and merge in AGS at 25.5 GeV
Dual harmonic RF
Bunch Split
Bunch Merge
h=12->6
Add a 1->2 bunch split during acceleration in the Booster
Reduces peak current at AGS injection by (optimally)
Requires a 2->1 merge at AGS extraction energy of 25 GeV to recovery the per bunch intensity
Present scheme:
A single pulse from the source remains a single bunch from source to collision
Booster and AGS injection both have defocusing RF harmonics

## Slide 5: Run 21 Split/merge test
500 ns
Time
h=1
h=2
h=3
Booster split
Booster RF:
Capture on h=1, defocus (h=2)
Accelerate to merge porch
Split h=1→h=2
‘Squeeze’ h=3 to get bunch spacing for BtA transfer
AGS Merge
h=6
h=12
h=6
AGS RF:
Capture on h=6, defocus (h=12)
Accelerate to flattop
Squeeze h=6 → 12
Merge h=12 → 6
200 ns
January 2021 pre-run test
Test the longitudinal mechanics
Basic unpolarized proton setup (no snakes)
Interleaved with two other proton efforts
Synch period at AGS flattop is 12 ms
  Merge takes a full second
  Hard to maintain constant, adiabatic conditions
In ~2 day test: 20% longitudinal emittance increase from merge

## Slide 6: RHIC Startup
Since both RHIC and the AGS startups are delayed, options are limited
RHIC setup
  Most of the ring can still be cooled: p.s. group doing checkout in all available areas as ready
  Some tests require fully cooled rings (high current checkout, shutoff tests) , cannot be done early
  Early tests could get us to 24/7 beam setup 1-2 days earlier in startup than normal
  Injection to physics in Run 17: 12 days with a modified lattice (no new lattice this year).
Injector setup:
  Booster setup of proton split and Au for CeC already done
  Aim to have the split-merge ready prior to physics declaration.