## Slide 1: RHIC Run 22 Startup Status 11/23/2021
RHIC and injectors startup teams planning toward the ‘projected earliest injection date:
  late evening Wed 12/1 (through 12/2 owl shift (0001-0800)
Startup progression (broadly)
  12/1-2 owl: Blue injection
  12/2-3 owl: Yellow injection
  12/3-4 owl: Ramps and pC setup
  12/5 day-eve : Rebucketing
  12/5-6 owl: Store setup
  Transition to overnight stores starts around here
Some CeC alignment work (using protons) to happen in parallel as much as possible.
Ops detailed schedule:
https://www.cadops.bnl.gov/AGS/Operations/OpsWiki/index.php/RHIC_Start-up_2022
9 am meetings starting Monday 11/29

## Slide 2
 | Wed 12/1 | 12/2 | Fri 12/3 | 12/4 | 12/5 | Mon 12/6 | 12/7 | 12/8 | 12/9
Owl |  | Blu inj/pC | Yel inj/pC | Ramps/pC | Ramps/pC | Store setup |  |  | 
Day | P.s. work |  |  | Rebucket |  | Ramp up and transition to physics |  |  | 
Eve | Blue inj |  |  | Rebucket |  |  |  |  | 
Aggressive timeline for RHIC startup 11/23/2021
Shifts | 
Owl | 0001-0800
Day | 0800-1600
Eve | 1600-2359
CeC beam-based alignment to take place in parallel with pC setup/conditioning where possible
Dec 6th and after days reserved for optimization and contingency:
  pC target finding conditioning: 12 hrs
  CeC BBA: 24 hours
  Very like that some pC conditioning and CeC work remains by 12/6+