## Slide 1
RHIC Run 22 Startup Status 12/07/2021
RHIC beam startup
  12/3 0100: First blue injection
  12/3 1400: PSEG lab power outage
    Every CAD facility affected
  12/6 ~0001 Yellow injection
  12/7 Ramp development (no beam to top energy yet).
  Outage probably immediately responsible for 1.5 to 2 day delay
CeC beam-based alignment interleaved
RHIC pC target positions set up (47 out of 48 available, 1 lost during setup)
Blue helical dipole damaged, possibly due to the power outage
  Outer coils can be run at high current to proved ~85% of the ideal spin rotation
  Requires
    re-establishing injection
    Change of other snake current
    Beam-based verification of new spin configuration
    Specialized tuning of trajectories during ramp to counter the additional imperfection resonance strength driven by suboptimal spin rotation in the snake.
Top priority is verifying that the partial snake configuration can provide a viable physics program.
  All other setup tasks are secondary